## KPI Summary
[10 empty] | Ocean | [5 empty] | Data | [5 empty] | Cap | [5 empty] | Phoenix | [5 empty] | Custom
Category of Metric | KPI Metric | YTD | Jul_2025 | Aug_2025 | Sep_2025 | Oct_2025 | Nov_2025 | Dec_2025 | Remarks | Jul_2025 | Aug_2025 | Sep_2025 | Oct_2025 | Nov_2025 | Dec_2025 | Jul_2025 | Aug_2025 | Sep_2025 | Oct_2025 | Nov_2025 | Dec_2025 | Jul_2025 | Aug_2025 | Sep_2025 | Oct_2025 | Nov_2025 | Dec_2025 | Jul_2025 | Aug_2025 | Sep_2025 | Oct_2025 | Nov_2025 | Dec_2025 | Jul_2025 | Aug_2025 | Sep_2025 | Oct_2025 | Nov_2025 | Dec_2025
Project Delivery Commitment | Schedule Adherence | 98.1166 | 96.494 | 99.1667 | 96.8389 | 98.2 | 98.25 | 99.75 |  | 89.47 | 100 | 93.75 | 100 | 100 | 100 | 100 | 95.8333 | 94.4444 | 92 |  |  | 98 | 100 | 99 | 99 | 96 | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 95 | 100 | 97 | 100 | 97 | 100
| Effort Adherence | 96.1177 | 93.4411 | 96.7333 | 93.25 | 97.532 | 97.5 | 98.25 |  | 89.47 | 100 | 81.25 | 100 | 100 | 100 | 88.2353 | 91.6667 | 100 | 91.66 |  |  | 99 | 98 | 99 | 100 | 100 | 97 | 93 | 94 | 89 | 96 | 93 | 96 | 97.5 | 100 | 97 | 100 | 97 | 100
| First Time Right Metric | 98.7725 | 98.3 | 99.66 | 97.525 | 99.4 | 98.5 | 99.25 |  | 100 | 100 | 90.625 | 97 | 100 | 100 | 100 | 100 | 100 | 100 |  |  | 99 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 92.5 | 98.3 | 97 | 100 | 94 | 97
Development Efficiency | Sprint Velocity | 98.1667 | 92 | 104 | 101.5 | 96.5 | 100.5 | 94.5 | [13 empty] | 89 | 75 | 88 | 88 | 89 | 76 | 95 | 133 | 115 | 105 | 112 | 113
| Code Review Coverage | 98.8333 | 100 | 96 | 100 | 98.5 | 98.5 | 100 | [13 empty] | 100 | 92 | 100 | 97 | 97 | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Effort Throughput (Estimated Effort of Stories Delivered to PQA) | 411.8333 | 740 | 421 | 533 | 110 | 554 | 113 | KPI available for Ocean Team alone
| Code Review Compliance (Tracks the number of merge commits submitted by developers versus those reviewed and approved) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | KPI available for Ocean Team alone
Speed of Development | Cycle time to Completion (Measures time from development start to completion) | 81.9 | 53.8 | 51.5 | 104.3 | 104.3 | 138 | 39.5 | KPI available for Ocean Team alone
Quality of Work | Defects per Epic / Story (Number of defects per epic or story) | 0.16528 | 0 | 0.125 | 0.16667 | 0.3 | 0.4 | 0 | KPI available for Ocean Team alone
| Customer Satisfaction Score | 4.1267 | 0 | 0 | 0 | 0 | 4.1267 | 0 |  | N/A | N/A | N/A | N/A | 3.75 | N/A | [10 empty] | 4.63 | [5 empty] | 4 | 0
Utilization Efficiency | Resource Utilization | 69.6838 | 76.4975 | 65.0225 | 69.555 | 61.5 | 74.295 | 71.2325 |  | 68.7 | 69.79 | 82.85 | 74.77 | 90.11 | 82.52 | [6 empty] | 90.85 | 83.09 | 85.87 | 73.27 | 83.32 | 73.47 | 87 | 77 | 72 | 61 | 80 | 72 | 59.44 | 30.21 | 37.5 | 36.96 | 43.75 | 56.94
| Attrition in the team | 7 | 0 | 1 | 5 | 1 | 0 | 0 |  | 0 | 1 | 1 | 0 | 0 | 0 |  |  |  | 1 |  |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Innovation / Team Proactiveness | New ideas generated to improve the Product | 11 | 6 | 3 | 2 | 0 | 0 | 0 | This KPI available for Phoneix & CAPTeam alone | 3 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 0 | 0
| Acceptance rate of submitted ideas / proposals | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stakeholder Feedback | Qualitative Comments / Feedback received during the monthly Retrospective sessions with stakeholders | 0 | Survey Not Initiated | Survey Not Initiated | Survey Not Initiated | Survey Not Initiated | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SR NOte (hidden)
Ocean team doesnot have Attriition details

## Ocean-Old (hidden)
Category | Key Performance Indicator | unit | KPI
|  |  | 2025-07-01 |  | 2025-08-01 |  | 2025-09-01 |  | 2025-10-01 |  | 2025-11-01
|  |  | Epic Level Details | Performance Result | Epic Level Details | Performance Result | Epic Level Details | Performance Result | Epic Level Details | Performance Result | Epic Level Details | Performance Result
Project Delivery | Schedule Adherence (% of Stories delivered within the committed timeline) | percentage | 19 (Stories delivered to PQA) | 89.47 | 15 (Stories delivered to PQA) | 100 | 16 (Stories delivered to PQA) | 93.75 | 10 (Stories delivered to PQA) | 100 | 8 (Stories delivered to PQA) | 100
| Effort Adherence (% of Stories delivered within the originally estimated efforts) | percentage | 19 (Stories delivered to PQA) | 89.47 | 15 (Stories delivered to PQA) | 100 | 16 (Stories delivered to PQA) | 81.25 | 10 (Stories delivered to PQA) | 100 | 8 (Stories delivered to PQA) | 100
| First Time Right (% of work delivered with minimal rework) | percentage | 6 (Stories deployed to production) | 100 | 8 (Stories deployed to production) | 100 | 24 (Stories deployed to production) | 90.625 | 13 (Stories deployed to production) | 97 | 15 (Stories deployed to production) | 100
Development Efficiency | Effort Throughput (Estimated Effort of Stories Delivered to PQA) | Hours | 19 (Stories delivered to PQA) | 740 | 15 (Stories delivered to PQA) | 421 | 16 (Stories delivered to PQA) | 533 | 10 (Stories delivered to PQA) | 110 | 8 (Stories delivered to PQA) | 554
| Code Review Compliance (Tracks the number of merge commits submitted by developers versus those reviewed and approved) | percentage | 19 (Stories delivered to PQA) | 100 | 15 (Stories delivered to PQA) | 100 | 16 (Stories delivered to PQA) | 100 | 10 (Stories delivered to PQA) | 100 | 8 (Stories delivered to PQA) | 100
Speed of development | Cycle time to Completion (Measures time from development start to completion) | days | 6 (Stories deployed to prod) | 53.8 | 8 (Stories deployed to prod) | 51.5 | 13 (Stories deployed to prod) | 104.3 | 13 (Stories deployed to prod) | 104.3 | 15 (Stories deployed to prod) | 138 | 9 stories belonged to Image Changes were worked from April 10th. The requirement ment for these came in bits and pieces
| Cycle time to PQA (Measures time from development start to PQA readiness) | days | 19 (Stories delivered to PQA) | 46.47 | 15 (Stories delivered to PQA) | 10.87 | 15 (Stories delivered to PQA) | 9.2 | 10 (Stories delivered to PQA) | 9.2 | 8 (Stories delivered to PQA) | 22.67
Quality of work | Defects per Epic / Story (Number of defects per epic or story) | bug per Epic | 6 (Stories deployed to prod) | 0 | 9 (Stories deployed to prod) | 0.125 | (Stories deployed to prod) | 0.16667 | (Stories deployed to prod) | 0.3 | 15 (Stories deployed to prod) | 0.4 | 6 bugs were found.
Utilization | Ocean's Utilization |  | 68.7 |  | 69.79 |  | 82.85 |  | 74.77 |  | 90.11
New Solutions
New Solutions | Number of new solutions suggested by Ocean |  | 1. Suggested Stability AI for implementing Image generation in eCards 2. Sugested and Demostrated Test Rigor. 3. Different Toold for Wcag
Stakeholder Feedback |  |  | 🟢Possitive Feedback |  | 🟢Possitive Feedback |  | 🟢Possitive Feedback |  |  |  | 3.75

## Ocean
Category | KPI | Applicable | Measure | Remarks | Unit | Benchmark | Target Score | 2025-07-01 |  | 2025-08-01 |  | 2025-09-01 |  | 2025-10-01 |  | 2025-11-01 |  | 2025-12-01 |  | 2026-01-01 |  | 2026-02-01 |  | 2026-03-01 |  | 2026-04-01 |  | 2026-05-01 |  | 2026-06-01
[8 empty] | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score
Project Delivery | Schedule Adherence | Yes | (% of Stories delivered within the committed timeline) | N/A | percentage | 90 | 95 | 19 (Stories delivered to PQA) | 89.47 | 15 (Stories delivered to PQA) | 100 | 16 (Stories delivered to PQA) | 93.75 | 10 (Stories delivered to PQA) | 100 | 8 (Stories delivered to PQA) | 100 | 3 (Stories delivered to PQA) | 100
| Effort Adherence | Yes | (% of Stories delivered within the originally estimated efforts) | N/A | percentage | 90 | 95 | 19 (Stories delivered to PQA) | 89.47 | 15 (Stories delivered to PQA) | 100 | 16 (Stories delivered to PQA) | 81.25 | 10 (Stories delivered to PQA) | 100 | 8 (Stories delivered to PQA) | 100 | 3 (Stories delivered to PQA) | 100
| First Time Right | Yes | (% of work delivered with minimal rework) | N/A | percentage | 90 | 92 | 6 (Stories deployed to production) | 100 | 8 (Stories deployed to production) | 100 | 24 (Stories deployed to production) | 90.625 | 13 (Stories deployed to production) | 97 | 15 (Stories deployed to production) | 100 | 4 (Stories deployed to production) | 100
Development Efficiency | Effort Throughput | Yes | (Estimated Effort of Stories Delivered to PQA) | N/A | Hours | N/A | N/A | 19 (Stories delivered to PQA) | 740 | 15 (Stories delivered to PQA) | 421 | 16 (Stories delivered to PQA) | 533 | 10 (Stories delivered to PQA) | 110 | 8 (Stories delivered to PQA) | 554 | 3 (Stories delivered to PQA) | 113
| Code Review Compliance | Yes | (Tracks the number of merge commits submitted by developers versus those reviewed and approved) | N/A | percentage | 90 | 95 | 19 (Stories delivered to PQA) | 100 | 15 (Stories delivered to PQA) | 100 | 16 (Stories delivered to PQA) | 100 | 10 (Stories delivered to PQA) | 100 | 8 (Stories delivered to PQA) | 100 | 3 (Stories delivered to PQA) | 100
Speed of development | Time to Market | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Cycle time to Completion | Yes | (Measures time from development start to completion) | N/A | days | 90 | 90 | 6 (Stories deployed to prod) | 53.8 | 8 (Stories deployed to prod) | 51.5 | 13 (Stories deployed to prod) | 104.3 | 13 (Stories deployed to prod) | 104.3 | 15 (Stories deployed to prod) | 138 | 4 (Stories deployed to prod) | 39.5
| Cycle time to PQA | Yes | (Measures time from development start to PQA readiness) | N/A | days | 30 | 30 | 19 (Stories delivered to PQA) | 46.47 | 15 (Stories delivered to PQA) | 10.87 | 15 (Stories delivered to PQA) | 9.2 | 10 (Stories delivered to PQA) | 9.2 | 8 (Stories delivered to PQA) | 22.67 | 3 (Stories delivered to PQA) | 16.33
| Non-Functional Cycle Time of completion | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Quality of work | Defects per Epic / Story | Yes | (Number of defects per epic or story) | N/A | bug per Epic | 0.5 | 0.5 | 6 (Stories deployed to prod) | 0 | 9 (Stories deployed to prod) | 0.125 | (Stories deployed to prod) | 0.16667 | (Stories deployed to prod) | 0.3 | 15 (Stories deployed to prod) | 0.4 | 4 (Stories deployed to prod) | 0
| Customer Satisfaction Score | No | N/A | N/A | N/A | N/A | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3.75 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Utilization | Utilization | Yes | Ocean's Utilization | N/A | N/A | 75 | 80 |  | 68.7 |  | 69.79 |  | 82.85 |  | 74.77 |  | 90.11 |  | 82.52
| Attrition | No | N/A | N/A | N/A | N/A | N/A |  | 0 | N/A | 1 | N/A | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Solutions | Number of new solutions/ideas suggested | Yes | Number of new solutions suggested by Ocean | N/A | N/A | N/A | 3 | 1. Suggested Stability AI for implementing Image generation in eCards 2. Sugested and Demostrated Test Rigor. 3. Different Toold for Wcag | 3
| Acceptance rate of submitted ideas / proposals | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Stakeholder Feedback | Qualitative Comments / Feedback received during the monthly Retrospective sessions with stakeholders | Yes | N/A | N/A | N/A | N/A | N/A | Possitive Feedback |  | Possitive Feedback |  | Possitive Feedback |  |  |  |  | 0

## Cap-Old (hidden)
Category of Metric | KPI Metric | Calculation Measure | Inputs | Target Score | Benchmark* | Red / Amber / Green Status | Remarks | Achieved Score
[8 empty] | FY26 YTD | July, 2025 | Aug, 2025 | Sep, 2025 | Oct, 2025 | Nov, 2025 | Dec, 2025 | Jan, 2026 | Feb, 2026 | Mar, 2026 | Apr, 2026 | May, 2026 | June, 2026
Project Delivery Commitment | Schedule Adherence | Tasks delivered as per committed schedule / Tasks delivered | 1. Actual Date = Date when the acceptance ticket is closed 2. Committed Date = Due Date for the Acceptance Ticket |  | 95% |  | Projects are driven from US, estimate and timelines are prposed by GTS (Alignment betwee US and GTS on Project timelines) | 98.4 | 98 | 100 | 99 | 99 | 96
| Effort Adherence | Tasks delivered as per committed schedule / Tasks delivered | 1. Actual Effort = Actual Effort of each issue ticket corresponding to the Epic that was delivered for PQA 2. Committed Effort = Planned Effort for each issue tickets corresponding to the Epic that was delivered for PQA |  | 95% |  |  | 99.2 | 99 | 98 | 99 | 100 | 100
| First Time Right Metric | % of all Prod movements where there were no Severity 1 and Severity 2 defects found in 4 weeks post delivery in Production Environment | 1. CR beyond 40 hours 2. CR Label to have "Reopen" 3. No Critical/High bugs post Product Release |  | 93% |  |  | 99.4 | 99 | 98 | 100 | 100 | 100
Development Efficiency | Sprint Velocity | Total Effort (or) Points of Delivered Stories / Total Effort (or) Points of planned Stories | 1. You need a list of all issues closed during the calendar month. 2.Total efforts from the issues closed/ Total planned effort from all the issues closed |  | Team-specific; consistency over time is key New Scrum Team 5-10 story points per person Typical Scrum Team 30-50 story points (total team) |  |  | 92.8667 | 92.6667 | 89.3333 | 101 | 92.3333 | 89
| Code Review Coverage | Total Code Reviewed by Specialist (preferred) or lead developer / Total Code committed |  |  | 70%–90% code coverage is generally considered good. 80% is general standard adopted by organizations |  |  | 97.2 | 100 | 92 | 100 | 97 | 97
Speed of Development | Time to market | Average Days from Requirements identification to market deployment | 1. From Date - Project approved 2. Date of Product release 3. Average of all of them |  | Varies widely; for software, TTM can range from 6 months to several years depending on complexity' |  | Template to capture (Project/CRs Identified, approved timestamp, planning started, development initiated, closure) | 0 | 0 | 0 | 0 | 0 | 0
| Cycle Time to completion | Average Days from Development initiation to deployment for feature development / enhancements to PQA | 1. For each, Closed date - Created date 2. Average of all of them |  | 45-60 days. Important to keep the feature size such that in 2 months turnaround, features are developed and delivered |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Non-Functional Cycle Time of completion | Average days from non-functional requirement identification to deployment to production | Specific to product ugprades, patches, etc., 1. For each, closed date - created date 2. Average of all of them |  | 75-90 days |  |  | 0 | 0 | 0 | 0 | 0 | 0
Quality of work | Customer Satisfaction Score | Average Score from Customer Satisfaction Surveys | Average Customer satisfaction score |  | 74% - 78% depending on the survey questions and rating scale adopted |  |  | 4.63 | 0 | 0 | 0 | 0 | 4.63
Utilization Efficiency | Resource Utilization | Total number of project hours / Total number of inventory hours | 1. Total Inventory Hours 2. Individual business productivity hours |  | 83.5% |  |  | 82.56 | 87 | 79 | 83 | 76.8 | 87
| Attrition in the team | Number of project associates with lesser than 12 months of experience in the project / Total number of associates in the project | Associates left the organization with the fiscal year |  | < 15% |  |  | 0.4 | 0 | 0 | 0.4 | 0 | 0
Innovation / Team Proactiveness | New ideas generated to improve the Product | Number of Proposals presented to Product Management team on improvement in Development Process / Features / technology stack | 1. New ideas to improve workflow/feature/process 2. Should be approved by India Business stakeholders |  | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Acceptance rate of submitted ideas / proposals | Total number of accepted proposals / total number of proposals submitted | Total submitted and Total Approved |  | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stakeholder Feedback | Qualitative Comments / Feedback received during the monthly Retrospective sessions with stakeholders | Typical Areas of retrospective 1. Communication effectiveness 2. Quality of Deliverables 3. Quality of clarifications raised during understanding of requirement phase etc.. | Quarterly Feedback during stakeholder connect 1. Feedback consolidated for a year |  | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Note on K7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Code Review label was not included in the Git tasks for code reviews during this sprint. Starting in October, this label will be added to track code review metrics.
Note on L7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Code Review label was not included in the Git tasks for code reviews during this sprint. Starting in October, this label will be added to track code review metrics.
Note on M7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Code Review label was not included in the Git tasks for code reviews during this sprint. Starting in October, this label will be added to track code review metrics.

## Cap
Category | KPI | Applicable | Measure | Remarks | Unit | Benchmark | Target Score | YTD | 2025-07-01 |  | 2025-08-01 |  | 2025-09-01 |  | 2025-10-01 |  | 2025-11-01 |  | 2025-12-01 |  | 2026-01-01 |  | 2026-02-01 |  | 2026-03-01 |  | 2026-04-01 |  | 2026-05-01 |  | 2026-06-01
[8 empty] | YTD | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score
Project Delivery | Schedule Adherence | Yes | Tasks delivered as per committed schedule/Tasks delivered | 1. Actual Date = Date when the acceptance ticket is closed 2. Committed Date = Due Date for the Acceptance Ticket |  | 90 | 95 | 98.5 |  | 98 |  | 100 |  | 99 |  | 99 |  | 96 |  | 99
| Effort Adherence | Yes | Tasks delivered as per committed schedule/Tasks delivered | 1. Actual Effort = Actual Effort of each issue ticket corresponding to the Epic that was delivered for PQA 2. Committed Effort = Planned Effort for each issue tickets corresponding to the Epic that was delivered for PQA |  | 90 | 95 | 98.8333 |  | 99 |  | 98 |  | 99 |  | 100 |  | 100 |  | 97
| First Time Right | Yes | % of all Prod movements where there were no Severity 1 and Severity 2 defects found in 4 weeks post delivery in Production Environment | 1. CR beyond 40 hours 2. CR Label to have "Reopen" 3. No Critical/High bugs post Product Release |  | 90 | 92 | 99.8333 |  | 99 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100
Development Efficiency | Sprint Velocity | Yes | Total Effort (or) Points of Delivered Stories / Total Effort (or) Points of planned Stories | 1. You need a list of all issues closed during the calendar month. 2.Total efforts from the issues closed/ Total planned effort from all the issues closed |  | Team-specific; consistency over time is key New Scrum Team 5-10 story points per person Typical Scrum Team 30-50 story points (total team) | 90 | 84.1667 |  | 89 |  | 75 |  | 88 |  | 88 |  | 89 |  | 76
| Code Review Coverage | Yes | Total Code Reviewed by Specialist (preferred) or lead developer / Total Code committed | N/A |  | 70%–90% code coverage is generally considered good. 80% is general standard adopted by organizations | 95 | 97.6667 |  | 100 |  | 92 |  | 100 |  | 97 |  | 97 |  | 100
Speed of development | Time to market | Yes | Average Days from Requirements identification to market deployment | 1. From Date - Project approved 2. Date of Product release 3. Average of all of them |  | Varies widely; for software, TTM can range from 6 months to several years depending on complexity' | N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Cycle time to Completion | Yes | Average Days from Development initiation to deployment for feature development / enhancements to PQA | 1. For each, Closed date - Created date 2. Average of all of them |  | 45-60 days. Important to keep the feature size such that in 2 months turnaround, features are developed and delivered | N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Non-Functional Cycle Time of completion | Yes | Average days from non-functional requirement identification to deployment to production | Specific to product ugprades, patches, etc., 1. For each, closed date - created date 2. Average of all of them |  | 75-90 days | N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Cycle time to PQA | No | N/A | N/A | N/A | N/A | N/A |  |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
Quality of work | Defects per Epic / Story | No | N/A | N/A | N/A | N/A | N/A |  |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
| Customer Satisfaction Score | Yes | Average Score from Customer Satisfaction Surveys | 74% - 78% depending on the survey questions and rating scale adopted |  | 74% - 78% depending on the survey questions and rating scale adopted | 4 | 0.926 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4.63
Utilization | Utilization | Yes | Total number of project hours / Total number of inventory hours | 1. Total Inventory Hours 2. Individual business productivity hours |  | 75% | 83.5% | 81.645 |  | 90.85 |  | 83.09 |  | 85.87 |  | 73.27 |  | 83.32 |  | 73.47
| Attrition | Yes | Number of project associates with lesser than 12 months of experience in the project / Total number of associates in the project | Associates left the organization with the fiscal year |  | < 15% |  | 4 |  | 0 |  | 0 |  | 4 |  | 0 |  | 0
Innovation / Team Proactiveness | Number of new solutions/ideas suggested | Yes | Number of new solutions suggested by Ocean | 1. New ideas to improve workflow/feature/process 2. Should be approved by India Business stakeholders |  | 2 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Acceptance rate of submitted ideas / proposals | Yes | Total number of accepted proposals / total number of proposals submitted | Total submitted and Total Approved |  | 2 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Stakeholder Feedback | Qualitative Comments / Feedback received during the monthly Retrospective sessions with stakeholders | Yes | Typical Areas of retrospective 1. Communication effectiveness 2. Quality of Deliverables 3. Quality of clarifications raised during understanding of requirement phase etc.. | Quarterly Feedback during stakeholder connect 1. Feedback consolidated for a year |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0

## Phoenix-Old (hidden)
Category of Metric | KPI Metric | Calculation Measure | Inputs | Target Score | Benchmark* | Red / Amber / Green Status | Remarks | Achieved Score
[8 empty] | FY26 YTD | July, 2025 | Aug, 2025 | Sep, 2025 | Oct, 2025 | Nov, 2025 | Dec, 2025 | Jan, 2026 | Feb, 2026 | Mar, 2026 | Apr, 2026 | May, 2026 | June, 2026
Project Delivery Commitment | Schedule Adherence | Total Epics (or) Stories delivered as per committed schedule / Total Epics (or) stories delivered | 1. You need a list of all stories updated during the calendar month 2. 'type = acceptance' to derive the epics that is delivered for PQA 3. Distrinct (epic_iids) with type=acceptance and the epic_iid is not yet closed indicates the total number of epics delivered for PQA 4. Actual Date = Date when the acceptance ticket is closed 5. Committed Date = Due Date for the Acceptance Ticket | 95% | 95% + | GREEN |  | 100 | 100 | 100 | 100 | 100 | 100
| Effort Adherence | Total Epics (or) Stories delivered as per committed Effort / Total Epics (or) stories delivered | 1. You need a list of all stories updated during the calendar month 2. 'type = acceptance' to derive the epics that is delivered for PQA 3. Distrinct (epic_iids) with type=acceptance and the epic_iid is not yet closed indicates the total number of epics delivered for PQA 4. Actual Effort = Actual Effort of each issue ticket corresponding to the Epic that was delivered for PQA 5. Committed Effort = Planned Effort for each issue tickets corresponding to the Epic that was delivered for PQA | 95% | 90% - 95% | AMBER |  | 93 | 93 | 94 | 89 | 96 | 93
| First Time Right Metric | % of all PPRD / Prod movements where there were no Severity 1 and Severity 2 defects found in 4 weeks post delivery in PPRD or Prod | 1. EL = Story that is also completed alone is considered 2. Epic_iid = (1) and then type = Bug, find the actual effort spent 3. Epic_iid = (1) and then Type != Bug, find the total effort spent 4. FTR = 1 - {(2)/(3)} | 95% | 90% - 95% | GREEN |  | 100 | 100 | 100 | 100 | 100 | 100
Development Efficiency | Sprint Velocity | Total Effort (or) Points of Delivered Stories / Total Effort (or) Points of planned Stories | 1. You need a list of all issues closed during the calendar month. 2.Total efforts from the issues closed/ Total planned effort from all the issues closed | 90% | Team-specific; consistency over time is key New Scrum Team 5-10 story points per person Typical Scrum Team 30-50 story points (total team) | GREEN |  | 112 | 95 | 133 | 115 | 105 | 112
| Code Review Coverage | Total Code Reviewed by Specialist (preferred) or lead developer / Total Code committed | Code Review and Merge is calculated git lab MR review process | 98% | 70%–90% code coverage is generally considered good. 80% is general standard adopted by organizations | GREEN |  | 100 | 100 | 100 | 100 | 100 | 100
Speed of Development | Time to market | Time to market | 1. You need a list of all stories closed during the calendar month 2. 'type = acceptance' to derive the epics that is delivered for PQA 3. For each, Epic's Closed date - Created date 4. Average of all of them | TBD | Varies widely; for software, TTM can range from 6 months to several years depending on complexity' | GREEN | Current GIT Tickets have age greated than 1 year and are being prioritized based on business needs. Need to discuss with Roshni on it | 83.2 | 73 | 99 | 103 | 46 | 95
Quality of Work | Defect Leakage | Total Defects post-release to PQA/PROD / Total number of Epics / Stories delivered | 1. List of all the issues with type ="bug" closed in given month where author =Andy 2. List of all the issues with type ="bug" closed in given month where author =Andy + List of all the issues with type ="bug" closed in given month where author =Suganya 3. Calculate {1}/{2} | 10% | 5% - 10% are considered good benchmarks |  |  | #DIV/0!
| Customer Satisfaction Score | Average Score from Customer Satisfaction Surveys | Average Customer satisfaction score | TBD | 74% - 78% depending on the survey questions and rating scale adopted | NA |  | 0 | 0 | 0 | 0 | 0 | 0
Utilization Efficiency | Resource Utilization | Total number of project hours / Total number of inventory hours |  | 78% | 65% -75% | AMBER |  | 75.4 | 87 | 77 | 72 | 61 | 80
| Attrition in the team | Number of project associates with lesser than 12 months of experience in the project / Total number of associates in the project |  | 10% | < 15% | GREEN | No Attrition | 0 | 0 | 0 | 0 | 0 | 0
Innovation / Team Proactiveness | New ideas generated to improve the Product | Number of Proposals presented to Product Management team on improvement in Development Process / Features / technology stack |  | 4 | 1 per quarter | GREEN | A total of 8 innovative ideas have been identified, focusing on automation, AI-driven intelligence, and system reliability.(Refer Ideas Sheet) | 1.6 | 3 | 3 | 2 | 0 | 0
| Acceptance rate of submitted ideas / proposals | Total number of accepted proposals / total number of proposals submitted |  | 1 | Atleast 1 accepted in the year |  |  | 0 | 0 | 0 | 0 | 0 | 0
Stakeholder Feedback | Qualitative Comments / Feedback received during the monthly Retrospective sessions with stakeholders | Typical Areas of retrospective 1. Communication effectiveness 2. Quality of Deliverables 3. Quality of clarifications raised during understanding of requirement phase etc.. |  |  |  |  | To be fillded based on Product Retrospective based on live Phoenix Onboarding from Delivery Team | 0.8 | 0 | 0 | 0 | 0 | 4
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Muruganandham Jayapal , Need splits how this % is derived Reply: Effort Adherence = (Actual Hours Tracked in IFS / Base Line Hours) * 100 Baseline hours : 690 Reply: This is wrong formula. The correct formula is Effort Adherence = No of Epics / stories delivered within estimated effort / Total number of epics / stories delivered Reply: @Muruganandham Jayapal - Pls correct this ASAP
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Muruganandham Jayapal , Need splits how this % is derived Reply: Effort Adherence = (Actual Hours Tracked in IFS / Base Line Hours) * 100 Baseline hours : 690 Reply: This is wrong formula. The correct formula is Effort Adherence = No of Epics / stories delivered within estimated effort / Total number of epics / stories delivered Reply: @Muruganandham Jayapal - Pls correct this ASAP
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Muruganandham Jayapal , Need splits how this % is derived Reply: Effort Adherence = (Actual Hours Tracked in IFS / Base Line Hours) * 100 Baseline hours : 690 Reply: This is wrong formula. The correct formula is Effort Adherence = No of Epics / stories delivered within estimated effort / Total number of epics / stories delivered Reply: @Muruganandham Jayapal - Pls correct this ASAP

## Phoenix
Category | KPI | Applicable | Measure | Remarks | Unit | Benchmark | Target Score |  | 2025-07-01 |  | 2025-08-01 |  | 2025-09-01 |  | 2025-10-01 |  | 2025-11-01 |  | 2025-12-01 |  | 2026-01-01 |  | 2026-02-01 |  | 2026-03-01 |  | 2026-04-01 |  | 2026-05-01 |  | 2026-06-01
[8 empty] | YTD | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score | Remarks | Score
Project Delivery | Schedule Adherence | Yes | Total Epics (or) Stories delivered as per committed schedule / Total Epics (or) stories delivered | 1. You need a list of all stories updated during the calendar month 2. 'type = acceptance' to derive the epics that is delivered for PQA 3. Distrinct (epic_iids) with type=acceptance and the epic_iid is not yet closed indicates the total number of epics delivered for PQA 4. Actual Date = Date when the acceptance ticket is closed 5. Committed Date = Due Date for the Acceptance Ticket |  | 90% | 95 | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100
| Effort Adherence | Yes | Total Epics (or) Stories delivered as per committed Effort / Total Epics (or) stories delivered | 1. You need a list of all stories updated during the calendar month 2. 'type = acceptance' to derive the epics that is delivered for PQA 3. Distrinct (epic_iids) with type=acceptance and the epic_iid is not yet closed indicates the total number of epics delivered for PQA 4. Actual Effort = Actual Effort of each issue ticket corresponding to the Epic that was delivered for PQA 5. Committed Effort = Planned Effort for each issue tickets corresponding to the Epic that was delivered for PQA |  | 90% | 95 | 95.0909 |  | 93 |  | 94 |  | 89 |  | 96 |  | 93 |  | 96 |  | 93 |  | 96 |  | 98 |  | 100 |  | 98
| First Time Right | Yes | % of all PPRD / Prod movements where there were no Severity 1 and Severity 2 defects found in 4 weeks post delivery in PPRD or Prod | 1. EL = Story that is also completed alone is considered 2. Epic_iid = (1) and then type = Bug, find the actual effort spent 3. Epic_iid = (1) and then Type != Bug, find the total effort spent 4. FTR = 1 - {(2)/(3)} |  | 90% | 92 | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100
Development Efficiency | Effort Throughput | Yes | Total Effort (or) Points of Delivered Stories / Total Effort (or) Points of planned Stories | 1. You need a list of all issues closed during the calendar month. 2.Total efforts from the issues closed/ Total planned effort from all the issues closed |  |  |  | 120.4545 |  | 95 |  | 133 |  | 115 |  | 105 |  | 112 |  | 113 |  | 109 |  | 115 |  | 162 |  | 155 |  | 111
| Code Review Compliance | Yes | Total Code Reviewed by Specialist (preferred) or lead developer / Total Code committed | Code Review and Merge is calculated git lab MR review process |  | 90 | 95 | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100
Speed of development | Time to market | Yes | Time to market | 1. You need a list of all stories closed during the calendar month 2. 'type = acceptance' to derive the epics that is delivered for PQA 3. For each, Epic's Closed date - Created date 4. Average of all of them |  | N/A | N/A | 83.2 |  | 73 |  | 99 |  | 103 |  | 46 |  | 95 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Cycle time to Completion | No
| Non-Functional Cycle Time of completion | No
| Cycle time to PQA | No
Quality of work | Defects per Epic / Story | No
| Customer Satisfaction Score | Yes | Average Score from Customer Satisfaction Surveys | Average Customer satisfaction score |  | 4 | 4 | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Utilization | Utilization | Yes | Total number of project hours / Total number of inventory hours | N/A |  | 75% | 78 | 76.9236 |  | 87 |  | 77 |  | 72 |  | 61 |  | 80 |  | 72 |  | 66.37 |  | 80.64 |  | 83.73 |  | 80.42 |  | 86
| Attrition | Yes | Number of project associates with lesser than 12 months of experience in the project / Total number of associates in the project | N/A |  | <15% | <10% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Innovation / Team Proactiveness | Number of new solutions/ideas suggested | Yes | Number of Proposals presented to Product Management team on improvement in Development Process / Features / technology stack | N/A |  | 2 | 3 | 8 |  | 3 |  | 3 |  | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| Acceptance rate of submitted ideas / proposals | Yes | Total number of accepted proposals / total number of proposals submitted | N/A |  | 2 | 3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
Stakeholder Feedback | Qualitative Comments / Feedback received during the monthly Retrospective sessions with stakeholders | Yes | Typical Areas of retrospective 1. Communication effectiveness 2. Quality of Deliverables 3. Quality of clarifications raised during understanding of requirement phase etc.. | N/A |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0

## Custom
Category | Key Performance Indicator | unit | KPI
|  |  | 2025-07-01 |  | 2025-08-01 |  | 2025-09-01 |  | 2025-10-25 |  | 2025-11-25 |  | 2025-12-25
|  |  | Issue Ticket Details | Performance Result | Issue Ticket Details | Performance Result | Issue Ticket Details | Performance Result | Issue Ticket Details | Performance Result | Issue Ticket Details | Performance Result | Issue Ticket Details | Performance Result
Product Delivery (US Delivery / India International Delivery) | Schedule Adherence ( Tickets Delivered on the planned scheduled date and time ) | percentage | 40 | 95 | 59 | 100 | 48 | 97 | 51 | 100 | 39 | 97 | 44 | 100
| Effort Adherence ( Tickets Delivered on the planned estimated time ) | percentage | 40 | 97.5 | 59 | 100 | 48 | 97 | 51 | 100 | 39 | 97 | 44 | 100
Development Efficiency | First Time Right ( Tickets Deliverered with the High Quality with first time delivery right ) | percentage | 40 | 92.5 | 59 | 98.3 | 48 | 97 | 51 | 100 | 39 | 94 | 44 | 97
Utilization | Custom Delivery Utilization |  |  | 59.44 |  | 30.21 |  | 37.5 |  | 36.96 |  | 43.75 |  | 56.94
New Solutions
New Solutions | Number of new solutions suggested by Shared Service

## Intelsuite
Category of Metric | KPI Metric | Calculation Measure | Measure | Target Score | Benchmark* | Red / Amber / Green Status | Remarks | Achieved Score
[8 empty] | FY26 YTD | July, 2025 | Aug, 2025 | Sep, 2025 | Oct, 2025 | Nov, 2025 | Dec, 2025 | Jan, 2026 | Feb, 2026 | Mar, 2026 | Apr, 2026 | May, 2026 | June, 2026
Project Delivery Commitment | Feature Completion Rate | Total Features delivered in the quarter / Total Features committed in the quarter × 100 | % | 90% | 90%+ |  |  | 70.5 | 75 | 75 | 75 | 66 | 66 | 66
| Schedule Adherence | Total Epics (or) Stories delivered as per committed schedule / Total Epics (or) stories delivered | % | 95% | 95% + |  |  | 91.1667 | 100 | 95 | 85 | 88 | 88 | 91
| Effort Adherence | Total Epics (or) Stories delivered as per committed Effort / Total Epics (or) stories delivered | % | 95% | 90% - 95% |  |  | 93.3333 | 94 | 95 | 100 | 88 | 88 | 95
Development Efficiency | Pipeline Success Rate | Successful runs / Total scheduled pipeline runs | % | ≥95% | 95%+ |  |  | 96.5 | 94 | 93 | 99 | 98 | 97 | 98
Quality of work | Platform Data Availability Rate | (Total Uptime of Gold Layer Data / Total Scheduled Uptime Window) × 100 | % | ≥ 99.5% | 99.5% – 99.9% |  |  | 99.5 | 100 | 97 | 100 | 100 | 100 | 100
| Data Quality Score | % of records passing validation rules for Data Completeness and Data Accuracy | % | 99% | Ensures confidence in insights |  |  | 99.6667 | 100 | 100 | 100 | 98 | 100 | 100
| Model Accuracy | Accuracy metric (e.g., F1, AUC, RMSE) based on business context | % | >85% | >90% |  |  | 85 | TBD | TBD | TBD | TBD | 85 | 85
| Model Drift Detection | % of models monitored for drift monthly | % | 100% | 100% |  |  | 0 | TBD | TBD | TBD | TBD | TBD
Innovation / Team Proactiveness | New ideas generated to improve the platform | Number of Proposals presented to the Product team on improvement in Development Process / Features / Technology stack | Count | ≥ 4 proposals/year | Aligned with business value |  |  | 3 |  | 1 | 1 | 1
| Acceptance rate of submitted ideas / proposals | Total number of accepted proposals / total number of proposals submitted | % | >= 20% | 20–40% optimal |  |  | 3 |  | 1 | 1 | 1
Stakeholder Feedback | Qualitative Comments / Feedback received during the monthly Retrospective sessions with stakeholders | Typical Areas of retrospective 1. Communication effectiveness 2. Quality of Deliverables 3. Quality of clarifications raised during understanding of requirement phase etc.. | Count | ≥ 4.0 | Avg. score (1–5) on communication, deliverables, clarity |  |  | 3.75 |  |  |  |  | 3.75
Note on J9: Sivakumar Moorthy: Model Accuracy will be measured from Q2 (Oct 2025)
Note on K9: Sivakumar Moorthy: Model Accuracy will be measured from Q2 (Oct 2025)
Note on L9: Sivakumar Moorthy: Model Accuracy will be measured from Q2 (Oct 2025)
Note on J10: Sivakumar Moorthy: Model Accuracy will be measured from Q2 (Oct 2025)
Note on K10: Sivakumar Moorthy: Model Accuracy will be measured from Q2 (Oct 2025)
Note on L10: Sivakumar Moorthy: Model Accuracy will be measured from Q2 (Oct 2025)
Note on J11: Sivakumar Moorthy: Model Drift Detection KPI will be measured from Q2 (Oct 2025)
Note on K11: Sivakumar Moorthy: Model Drift Detection KPI will be measured from Q2 (Oct 2025)
Note on L11: Sivakumar Moorthy: Model Drift Detection KPI will be measured from Q2 (Oct 2025)

## Tsgeast
Category of Metric | KPI Metric | Calculation Measure | Target Score | Benchmark* | Red / Amber / Green Status | Remarks | Achieved Score
[7 empty] | FY26 YTD | July, 2025 | Aug, 2025 | Sep, 2025 | Oct, 2025 | Nov, 2025 | Dec, 2025 | Jan, 2026 | Feb, 2026 | Mar, 2026 | Apr, 2026 | May, 2026 | June, 2026
Project Delivery Commitment | Schedule Adherence | Total Epics (or) Stories delivered as per committed schedule / Total Epics (or) stories delivered |  | 95% + |  |  | 96.6667 | 100 | 96 | 92 | 92 | 100 | 100
| Effort Adherence | Total Epics (or) Stories delivered as per committed Effort / Total Epics (or) stories delivered |  | 90% - 95% |  |  | 92.5 | 90 | 96 | 96 | 92 | 88 | 93
| First Time Right Metric | % of all PPRD / Prod movements where there were no Severity 1 and Severity 2 defects found in 4 weeks post delivery in PPRD or Prod |  | 90% - 95% |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100
Development Efficiency | Code Review Coverage | Total Code Reviewed by Specialist or lead developer / Total Code committed |  | 70%–90% code coverage is generally considered good. 80% is general standard adopted by organizations |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100
Quality of Work | Customer Satisfaction Score | Average Score from Customer Satisfaction Surveys |  | 74% - 78% depending on the survey questions and rating scale adopted |  |  | 0 | TBD | TBD | TBD | TBD | TBD | TBD
Innovation / Team Proactiveness | New ideas generated to improve the Product | Number of Proposals presented to Product Management team on improvement in Development Process / Features / technology stack |  |  |  |  | 1 |  | 1
| Acceptance rate of submitted ideas / proposals | Total number of accepted proposals / total number of proposals submitted |  |  |  |  | 1 |  | 1
Stakeholder Feedback | Qualitative Comments / Feedback received during the monthly Retrospective sessions with stakeholders | Typical Areas of retrospective 1. Communication effectiveness 2. Quality of Deliverables 3. Quality of clarifications raised during understanding of requirement phase etc.. |  |  |  |  | 3.75 |  |  |  |  | 3.75
Note on I8: Sivakumar Moorthy: Identified gaps in existing Goodman process due to data inconsistency. Estimate provided to enhance and fill these gaps.
Note on I9: Sivakumar Moorthy: Identified gaps in existing Goodman process due to data inconsistency. Estimate provided to enhance and fill these gaps.
Note on I10: Sivakumar Moorthy: Identified gaps in existing Goodman process due to data inconsistency. Estimate provided to enhance and fill these gaps.

## Data
Project | Total Issues/Features | Schedule Adherence % | Effort Adherence % | Quality Score
Jul | 17 | 100% | 88.24% | 100%
Aug | 24 | 95.83% | 91.67% | 100%
Sep | 18 | 94.44% | 100% | 100%
Grand Total | 59 | 96.61% | 93.22% | 100%
Project | Total Issues/Features | Schedule Adherence % | Effort Adherence % | Quality Score
Jul | 17 | 100 | 88.2353 | 100
Aug | 24 | 95.8333 | 91.6667 | 100
Sep | 18 | 94.4444 | 100 | 100
Grand Total | 59 | 96.6102 | 93.2203 | 100
Oct 2025 | Issue/Feature Handled | Schedule Adherence % | Effort Adherence % | Quality Score
carrier-bryant | 3 | 100% | 100% | 100%
Coke - Distributor Leads | 2 | 100% | 100% | 100%
cost-system | 3 | 66.67% | 100% | 100%
Goodman | 3 | 100% | 66.67% | 100%
Marketing Database | 1 | 100% | 100% | 100%
Grand Total | 12 | 92 | 91.66 | 100
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.