## Dashboard
FY27 ENGINEERING EXECUTIVE DASHBOARD | [6 empty] | CHART DATA (do not delete)
Governance view ¦ 01 Jul 2026 – 30 Jun 2027 ¦ All KPIs formula-linked to Project Tracker · Refresh values by recalculating workbook
[7 empty] | Status | Count
| Total Projects | Total Tasks | Completed | In Progress | Blocked | At Risk | Not Started
In Progress
Completed
| Overall Progress % | Hours Planned | Hours Actual | Budget Consumed | Upcoming Milestones | Overdue Dependencies | At Risk
Blocked
[7 empty] | Owner | Tasks
Jawahar
Kadarkarai
MJ
Shriguru
Siva
[7 empty] | Month | Cumulative Completed % | Planned Burn-up %
[7 empty] | 2026-07-01 |  | 8.333%
[7 empty] | 2026-08-01 |  | 16.67%
[7 empty] | 2026-09-01 |  | 25%
[7 empty] | 2026-10-01 |  | 33.33%
[7 empty] | 2026-11-01 |  | 41.67%
[7 empty] | 2026-12-01 |  | 50%
[7 empty] | 2027-01-01 |  | 58.33%
[7 empty] | 2027-02-01 |  | 66.67%
[7 empty] | 2027-03-01 |  | 75%
[7 empty] | 2027-04-01 |  | 83.33%
[7 empty] | 2027-05-01 |  | 91.67%
[7 empty] | 2027-06-01 |  | 100%
[7 empty] | Release | Avg % Complete
R26.Q1
| Resource Utilization (see Resource Planning sheet for heatmap & detail) | [5 empty] | R26.Q2
| Avg Utilization | [5 empty] | R26.Q3
| Overallocated Resources | [5 empty] | R26.Q4
R27.Q1
| LINE CHART — Progress trend uses Monthly Burn-up above. | [5 empty] | R27.Q2
Hotfix
| STATUS LEGEND | HOW TO USE |  |  |  |  | N/A
| Completed | 1. Update Project Tracker (status, dates, hours) — Dashboard KPIs refresh automatically.
| In Progress | 2. Maintain dropdown values on Lookup Lists sheet (named ranges).
| At Risk | 3. Review Gantt Chart weekly; orange ▶ marks current week.
| Blocked | 4. Clear overdue Dependencies and High/Critical Risks in governance.
| Not Started | 5. Print Dashboard / Tracker in Landscape for CTO pack.
Formulas:
Cumulative Completed % = IFERROR(COUNTIFS('Project Tracker'!$M5:M113,"Completed",'Project Tracker'!$O5:O113,"<="&EOMONTH([Month],0))/COUNTA('Project Tracker'!$A5:A113),0)

## Project Tracker
FY27 ENGINEERING PROJECT TRACKER
Source: plan/FY 27 Draft Planning.xlsx · FY27 V1 ¦ Plan window: 2026-07-01 → 2027-06-30 ¦ Formula-driven ¦ Weekly governance ready
Task ID | Epic | Project | Feature | Sprint | Phase | Workstream | Task Name | Description | Owner | Team | Priority | Status | Start Date | End Date | Duration | % Complete | Planned Hours | Actual Hours | Variance | Budget | Dependency | Blocked By | Risk | Next Action | Target Release | Remarks | Critical Path
T-001 | CS 1.0 — Maintenance | CS 1.0 | Maintenance | Sprint 01 | Release | Reliability | Shutting down BRIKS service from Nackle | Pending action to completely remove BRIKS services from Nackle ecosystem | MJ | Core Product | High | At Risk | 2026-09-22 | 2026-09-28 |  | 13% | 40 | 5.9 |  | 4400 |  |  | R-19 | Clarify Include/Pending decision; rebaseline if needed | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-002 | CS 1.0 — Maintenance | CS 1.0 | Maintenance | Sprint 02 | Release | Reliability | Shutting Down Coupon/OTP Services | Testing and Any support needed(Ensure all existing application 1X and 2.0 work as expected) | MJ | Core Product | High | In Progress | 2026-07-10 | 2026-07-23 |  | 36% | 40 | 14.6 |  | 4400 | T-001 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 ¦ Hours=TBD in source | No
T-003 | CS 1.0 — Funct Enhance | CS 1.0 | Funct Enhance | Sprint 03 | Design | Product Delivery | Integrate the email validation service for Channel Smart 1.0(Roshni to check) | Handle the self registration and bulk load scneario | MJ | Core Product | High | In Progress | 2026-08-02 | 2026-08-08 |  | 36% | 40 | 14 |  | 4400 | T-002 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-004 | CS 1.0 — Funct Enhance | CS 1.0 | Funct Enhance | Sprint 04 | Design | Product Delivery | Build Unsubscribe feature for all the promotional emails(Roshni to check) | Build Unsubscribe feature for all the promotional emails | MJ | Core Product | High | Not Started | 2026-08-01 | 2026-08-10 |  | 0% | 60 | 0 |  | 6600 | T-003 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-005 | CS 1.0 — New Features | CS 1.0 | New Features | Sprint 05 | Build | Product Delivery | Cash + Wallet + Compliance - Integration patch for CS 1.0 | Integrating the Cash/Wallet/Compliance to Existing 1.0 Customers | MJ | Core Product | High | Not Started | 2026-08-01 | 2026-09-02 |  | 0% | 200 | 0 |  | 22000 | T-004 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=July | No
T-006 | CS 2.0 — Funct Enhance | CS 2.0 | Funct Enhance | Sprint 06 | Design | Product Delivery | Build Pipeline for Achievo to be updated |  | MJ | Core Product | High | Not Started | 2026-09-17 | 2026-09-26 |  | 0% | 40 | 0 |  | 4400 |  |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=July ¦ Hours=TBD in source | No
T-007 | CS 2.0 — Funct Enhance | CS 2.0 | Funct Enhance | Sprint 01 | Design | Product Delivery | Integrate the email validation service for Channel Smart 2.0(Roshni to check) | Handle the self registration and bulk load scneario | MJ | Core Product | High | Not Started | 2026-08-23 | 2026-08-29 |  | 0% | 40 | 0 |  | 4400 | T-006 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-008 | CS 2.0 — Funct Enhance | CS 2.0 | Funct Enhance | Sprint 02 | Design | Product Delivery | Build Unsubscribe feature for all the promotional emails(Roshni to check) | Build Unsubscribe feature for all the promotional emails | MJ | Core Product | High | Not Started | 2026-08-26 | 2026-09-04 |  | 0% | 60 | 0 |  | 6600 | T-007 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-009 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 03 | Build | Product Delivery | ERP Connerctor Service(Saleforce) |  | MJ | Core Product | High | Not Started | 2026-07-01 | 2026-08-27 |  | 0% | 350 | 0 |  | 38500 | T-008 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-010 | CS 2.0 — Tech Maintenance | CS 2.0 | Tech Maintenance | Sprint 04 | Hypercare | Reliability | Technology refresh | Mandatory adoption of newer tools and frameworks Phoenix - Platform Site Upgrades (Onetime) To 16.x Admin - Platform Site Upgrades (Onetime) To 16.x | Jawahar | Core Product | High | In Progress | 2026-08-31 | 2026-09-12 |  | 29% | 80 | 26.3 |  | 8800 | T-009 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-011 | CS 2.0 — Tech Maintenance | CS 2.0 | Tech Maintenance | Sprint 05 | Hypercare | Reliability | Fix for Critical Performance Issue(Claims, File Upload) | Top 10 recommendations and Performance Fix to be applied for the existing high priority issues. | Jawahar | Core Product | High | In Progress | 2026-09-06 | 2026-09-19 |  | 22% | 40 | 9.5 |  | 4400 | T-010 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=July ¦ Hours=TBD in source | No
T-012 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 06 | Build | Product Delivery | Build a game engine - Requirements | N/A | MJ | Core Product | High | Not Started | 2026-07-05 | 2026-07-14 |  | 0% | 60 | 0 |  | 6600 | T-011 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-013 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 01 | Build | Product Delivery | BRD Composer | BRD Composer | MJ | Core Product | High | In Progress | 2026-08-03 | 2026-09-21 |  | 24% | 300 | 76.5 |  | 33000 | T-012 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-014 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 02 | Build | Product Delivery | Communication connector which can support the Whatsapp and Wechat communicaton bi direction |  | MJ | Core Product | High | Not Started | 2026-07-09 | 2026-09-16 |  | 0% | 600 | 0 |  | 66000 | T-013 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-015 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 13 | Build | Product Delivery | AI-Powered Claim Validation | Introduce AI-assisted claim validation capabilities leveraging intelligent document processing to automate claim ingestion, extraction, validation, routing, and continuous learning. Strategic FY27 initiative under evaluation. | MJ | Core Product | High | Not Started | 2027-01-23 | 2027-02-01 |  | 0% | 40 | 0 |  | 4400 |  |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 ¦ Hours=TBD in source | No
T-016 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 22 | Build | Product Delivery | MDF Budget Management & Incentivization | Develop end-to-end MDF request, approval, budget allocation, campaign setup, and incentive distribution capabilities to improve fund utilization and business outcome tracking. Strategic FY27 initiative under evaluation. | MJ | Core Product | High | At Risk | 2027-05-28 | 2027-06-06 |  | 9% | 40 | 3.4 |  | 4400 | T-015 |  | R-14 | Clarify Include/Pending decision; rebaseline if needed | N/A | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-017 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 23 | Build | Product Delivery | AI Display Audit & Compliance Management | Implement AI-powered image analysis to automate display compliance audits, validate merchandising standards, and improve audit scalability, accuracy, and efficiency. Strategic FY27 initiative under evaluation. | MJ | Core Product | High | Blocked | 2027-04-05 | 2027-05-02 |  | 14% | 40 | 5.6 |  | 4400 | T-016 | T-016 | R-20 | Resolve blocker with dependency owner | N/A | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-018 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 24 | Build | Product Delivery | Organization-Centric Loyalty Journey | Enable partner organizations to participate in loyalty and incentive programs through organization onboarding, governance controls, centralized reward management, and organization-led participation models. Strategic FY27 initiative under evaluation. | MJ | Core Product | High | At Risk | 2027-04-23 | 2027-05-20 |  | 5% | 40 | 1.9 |  | 4400 | T-017 |  | R-09 | Clarify Include/Pending decision; rebaseline if needed | N/A | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-019 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 25 | Build | Product Delivery | Social Advocacy & Partner Influence Platform | Enable partners to share approved brand content, track engagement and attribution, and participate in incentive-driven advocacy programs that extend brand reach and influence. Strategic FY27 initiative under evaluation. | MJ | Core Product | High | At Risk | 2027-04-23 | 2027-05-13 |  | 20% | 40 | 7.7 |  | 4400 | T-018 |  | R-09 | Clarify Include/Pending decision; rebaseline if needed | N/A | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-020 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 26 | Build | Product Delivery | Partner Referral & Growth Engine | Establish a referral ecosystem with attribution tracking, milestone-based rewards, referral analytics, and conversion visibility to support partner-led acquisition and network-driven growth. Strategic FY27 initiative under evaluation. | MJ | Core Product | High | At Risk | 2027-06-06 | 2027-06-15 |  | 12% | 40 | 4.3 |  | 4400 | T-019 |  | R-18 | Clarify Include/Pending decision; rebaseline if needed | N/A | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-021 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 26 | Build | Product Delivery | AI-Powered Audience Segmentation | Enable business users to create audience segments using natural language queries across transactional, behavioral, and engagement data, improving campaign targeting and intervention effectiveness. Strategic FY27 initiative under evaluation. | MJ | Core Product | High | At Risk | 2027-05-06 | 2027-06-02 |  | 7% | 40 | 2.7 |  | 4400 | T-020 |  | R-02 | Clarify Include/Pending decision; rebaseline if needed | N/A | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-022 | CS 2.0 — New Features | CS 2.0 | New Features | Sprint 22 | Build | Product Delivery | Embedded Gamification Experiences | Introduce contextual, embedded gaming experiences within partner journeys to increase engagement, accelerate reward cycles, encourage repeat interactions, and improve program participation. Strategic FY27 initiative under evaluation. | MJ | Core Product | High | At Risk | 2027-05-21 | 2027-05-30 |  | 15% | 40 | 6.2 |  | 4400 | T-021 |  | R-06 | Clarify Include/Pending decision; rebaseline if needed | N/A | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-023 | CS 2.0 Achievo — Funct Enhance | CS 2.0 Achievo | Funct Enhance | Sprint 03 | Design | Product Delivery | Achievo - UI/UX Improvements | UI/UX improvements based on External recommendations | Shriguru | Rewards | Critical | Not Started | 2026-08-02 | 2026-08-22 |  | 0% | 40 | 0 |  | 4400 |  |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 ¦ Hours=TBD in source | No
T-024 | CS 2.0 Achievo — Tech Maintenance | CS 2.0 Achievo | Tech Maintenance | Sprint 04 | Hypercare | Reliability | Achievo - Mobile Performance Improvement.(Analysis) | Overall Mobile Performance Recommendations | Shriguru | Rewards | Critical | In Progress | 2026-07-11 | 2026-07-15 |  | 29% | 24 | 6.5 |  | 2640 | T-023 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | Yes
T-025 | CS 2.0 Achievo — Tech Maintenance | CS 2.0 Achievo | Tech Maintenance | Sprint 05 | Hypercare | Reliability | Achievo - Mobile Performance Improvement.(Implementation) | Overall Mobile Performance Improvements | Shriguru | Rewards | Critical | In Progress | 2026-09-13 | 2026-09-22 |  | 24% | 40 | 8.8 |  | 4400 | T-024 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 ¦ Hours=TBD in source | Yes
T-026 | CS 2.0 Achievo — Tech Maintenance | CS 2.0 Achievo | Tech Maintenance | Sprint 06 | Hypercare | Reliability | Achievo - Android 16 Upgrade | Achievo - Android 16 Upgrade. | Shriguru | Rewards | High | Not Started | 2026-08-31 | 2026-09-06 |  | 0% | 40 | 0 |  | 4400 | T-025 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-027 | CS 2.0 Achievo — Tech Maintenance | CS 2.0 Achievo | Tech Maintenance | Sprint 01 | Hypercare | Reliability | Achievo - iOS Updates | N/A | Shriguru | Rewards | High | In Progress | 2026-07-16 | 2026-07-22 |  | 11% | 40 | 4.2 |  | 4400 | T-026 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-028 | CS 2.0 Achievo — New Features | CS 2.0 Achievo | New Features | Sprint 23 | Build | Product Delivery | Achievo Mobile Experience Modernization | Modernize Achievo with mobile-native capabilities including push notifications, voice-assisted discovery, enhanced UX, QR-enabled interactions, gamification, and AI-assisted workflows to increase engagement and participation. Strategic FY27 initiative under evaluation. | Shriguru | Rewards | High | At Risk | 2027-05-08 | 2027-05-21 |  | 24% | 40 | 10.6 |  | 4400 | T-027 |  | R-04 | Clarify Include/Pending decision; rebaseline if needed | N/A | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-029 | CS 2.0 — Funct Enhance | CS 2.0 | Funct Enhance | Sprint 24 | Design | Product Delivery | Existing Product Backlog and Delivery Priority Items as needed to be added to Core Product | Need to work with Roshni to identify Priority items to be taken into Core | MJ | Core Product | High | Blocked | 2027-06-11 | 2027-06-20 |  | 15% | 40 | 6 |  | 4400 | T-022 | T-022 | R-03 | Resolve blocker with dependency owner | N/A | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-030 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 02 | Build | Platform | New UI for platform portal |  | MJ | Platform | High | Not Started | 2026-08-28 | 2026-09-23 |  | 0% | 160 | 0 |  | 17600 |  |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-031 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 03 | Build | Product Delivery | Architecture Proposal: Core + Extension Model for Participant Portals | Define a Core + Extension architecture model for Participant Portals to separate common product capabilities from client-specific customizations. This will help reduce the effort required to apply latest product changes across multiple delivery deployments, minimize the risk of overriding existing client-specific features, and improve maintainability, upgradeability, and release consistency across implementations. | MJ | Platform | Critical | Not Started | 2026-07-06 | 2026-09-13 |  | 0% | 600 | 0 |  | 66000 | T-030 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=July | No
T-032 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 04 | Build | Product Delivery | File Upload Module Stabilization and Validation Enhancements (Check if it can be moved to Q2) | Enhance the existing File Upload Module with improved validation, tracking, retry handling, and stabilization capabilities. This will improve upload reliability, reduce processing failures, provide better visibility into upload status, support controlled reprocessing, and strengthen the overall stability of file-based data ingestion. | MJ | Platform | Critical | Not Started | 2026-07-12 | 2026-09-19 |  | 0% | 600 | 0 |  | 66000 | T-031 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=July | No
T-033 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 05 | Hypercare | Reliability | Release Governance, Code Merge and Deployment Control | Standardize the code merge and release management process by improving version control, conflict handling, release planning, approvals, deployment tracking, rollback governance, and client-specific patch management. This will strengthen engineering governance, reduce release risks, and improve operational control across releases. | Jawahar | Platform | High | In Progress | 2026-08-09 | 2026-09-14 |  | 22% | 220 | 43.9 |  | 24200 | T-032 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-034 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 06 | Hypercare | Reliability | Achievo Mobile App Upgrades and Store Policy Compliance Updates | Perform Achievo mobile app upgrades and store-specific policy updates for iOS and Android. This includes updating SDKs, dependencies, build tools, privacy/permission declarations, App Store and Play Store compliance requirements, testing, build validation, and supporting app submission/review activities. | Jawahar | Platform | Critical | Not Started | 2026-07-22 | 2026-09-12 |  | 0% | 320 | 0 |  | 35200 | T-033 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-035 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 01 | Hypercare | Reliability | Next.js 16.x LTS Upgrade for Admin Console and Platform Web Apps | Upgrade Next.js to Version 16.x LTS (Admin & Platform) - 14.X is already outdated and 15.x is reaching end of life by 21/Oct/2026 | Jawahar | Platform | Critical | Not Started | 2026-08-22 | 2026-09-27 |  | 0% | 220 | 0 |  | 24200 | T-034 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=July | No
T-036 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 02 | Build | Platform | Scalable File Upload Processing Enhancement | Enhance the existing file upload processing architecture to handle large files with more than 100,000 records. This will address the current single-pod stateful processing limitation by improving scalability, reliability, and fault tolerance for high-volume uploads | MJ | Platform | Critical | Not Started | 2026-07-23 | 2026-08-21 |  | 0% | 180 | 0 |  | 19800 | T-035 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-037 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 03 | Build | Product Delivery | AWS Secrets Manager Enforcement for Service Credentials | Enforce AWS Secrets Manager usage for all service credentials and remove any plain-text or insecure storage of credentials from configuration files, environment variables, deployment scripts, and service-level settings. This will improve credential security, strengthen governance, reduce secret exposure risk, and align services with secure configuration management practices. | MJ | Platform | Critical | In Progress | 2026-07-06 | 2026-08-01 |  | 42% | 160 | 58.7 |  | 17600 | T-036 |  | R-01 | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | Yes
T-038 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 04 | Hypercare | Reliability | SAST Vulnerability Fixes Based on GitLab Security Findings | SAST Fixes - As per the GitLab analysis results - Review and fix SAST vulnerabilities reported through GitLab security scans for the existing codebase. Although new vulnerabilities are controlled through MR-level gates, additional findings may arise from updated scan rules, new CVEs, dependency changes, or existing code risks. This includes validation, prioritization, remediation, retesting, and closure tracking in GitLab. | Jawahar | Platform | Critical | In Progress | 2026-07-30 | 2026-08-18 |  | 29% | 120 | 35.9 |  | 13200 | T-037 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=July | Yes
T-039 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 05 | Hypercare | Reliability | Kubernetes Resource Optimization | Review EKS resource requests/limits, autoscaling, pod disruption budgets, node utilization, and cost/performance tuning. | Jawahar | Platform | Critical | In Progress | 2026-08-31 | 2026-09-19 |  | 34% | 120 | 39.2 |  | 13200 | T-038 |  | R-18 | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | Yes
T-040 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 06 | Hypercare | Reliability | Infrastructure and Application Monitoring for EKS Platform | Infrastructure and Application Monitoring - Monitor the AWS EKS-based infrastructure and application ecosystem using Grafana and related monitoring tools. This includes tracking cluster health, service availability, resource usage, application performance, API response times, worker status, error trends, and alerts, along with coordinating corrective actions to maintain platform stability and availability. | Jawahar | Platform | Critical | In Progress | 2026-08-05 | 2026-08-20 |  | 30% | 96 | 25.9 |  | 10560 | T-039 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | Yes
T-041 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 01 | Hypercare | Reliability | Application Issue Fixes and Remediation | Issue Fixes - Analyse and fix application issues reported by delivery, internal, QA, or support teams outside planned feature implementation. This includes root cause analysis, required code/configuration fixes, validation, retesting support, and release through the planned delivery process. | Jawahar | Platform | Critical | In Progress | 2026-07-18 | 2026-09-25 |  | 41% | 420 | 197.1 |  | 46200 | T-040 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | Yes
T-042 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 02 | Hypercare | Reliability | GitLab DAST Enablement for Web Application and Admin Console | Enable DAST for all the deployable services - Enable GitLab DAST for the Web Application and Admin Console to perform runtime vulnerability scanning as part of the GitLab DevSecOps pipeline. This will help identify security issues in deployed application flows and improve release-level security validation | Jawahar | Platform | High | Not Started | 2026-08-08 | 2026-08-14 |  | 0% | 40 | 0 |  | 4400 | T-041 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-043 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 03 | Hypercare | Reliability | Release Management, Regression Testing and Test Automation | Release Management Activities - Regression Testing & Automation - Manage release activities, coordinate deployments, perform regression testing, maintain automation scripts, validate fixes, support release sign-off, and monitor post-release stability. This includes improving regression automation coverage to reduce manual effort and improve release quality. Note: Reduced this effort considering the release maangement will also go to the respective features, for the delivery customization this will be part of the delivery budget | Kadarkarai | Platform | Critical | Not Started | 2026-09-04 | 2026-09-28 |  | 0% | 150 | 0 |  | 16500 | T-042 |  | R-03 | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-044 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 04 | Hypercare | Reliability | Performance Testing, Tuning and Test Suite Management | Perform performance testing as per the planned test schedule, followed by performance fine-tuning, regression testing, test suite maintenance, fixture updates, and automation improvements. This includes adding or removing test fixtures, maintaining test scripts, validating performance improvements, and ensuring the test suite remains aligned with application changes. Note: Reduced this effort considering the release maangement will also go to the respective features | Kadarkarai | Platform | High | Not Started | 2026-07-20 | 2026-08-13 |  | 0% | 150 | 0 |  | 16500 | T-043 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-045 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 05 | Hypercare | Reliability | DevOps Management, Improvements and Pipeline Monitoring | Devops Management/Improvement/Monitoring - Manage and improve the existing DevOps setup by enhancing CI/CD pipelines, adding new deployment workflows, optimizing automation, monitoring pipeline health, troubleshooting deployment issues, and supporting DevOps changes required for new services, environments, and platform upgrades. | Jawahar | Platform | Critical | Not Started | 2026-08-12 | 2026-08-17 |  | 0% | 36 | 0 |  | 3960 | T-044 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-046 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 06 | Hypercare | Reliability | Release Based Feature Documentation | Create release based feature documentation covering new features, functional changes, configuration steps, usage flows, dependencies, screenshots, and known limitations. This will support delivery, QA, support, product, and implementation teams in understanding and adopting each release | Jawahar | Platform | Critical | Not Started | 2026-07-08 | 2026-07-13 |  | 0% | 36 | 0 |  | 3960 | T-045 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-047 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 01 | Hypercare | Reliability | Monthly Library Upgrade Assessment and Remediation Across Services | Perform monthly scheduled library and package upgrade assessment across 20+ services, including web apps, Node.js services, workers, and .NET services. This includes identifying available upgrades, assessing security and compatibility impact, handling breaking changes, applying required fixes, validating builds, and supporting regression/release readiness. | Jawahar | Platform | Critical | In Progress | 2026-07-16 | 2026-07-20 |  | 34% | 30 | 10.5 |  | 3300 | T-046 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | Yes
T-048 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 02 | Hypercare | Reliability | Cloud Usage Chargeback Model, Monthly Tenant-Level Allocation | Cloud Usage Charge back model (Monthly) - Prepare monthly tenant-level cloud usage chargeback by collecting cloud consumption data, applying agreed allocation rules, validating usage/cost anomalies, and publishing the monthly chargeback summary for each tenant. | Jawahar | Platform | Critical | In Progress | 2026-07-11 | 2026-07-15 |  | 25% | 12 | 2.8 |  | 1320 | T-047 |  | R-20 | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | Yes
T-049 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 07 | Hypercare | Reliability | Internal VAPT - Half-Yearly Penetration Testing and Fixes | Perform half-yearly internal VAPT between yearly external VAPT cycles to proactively identify and fix security issues. This includes internal penetration testing, finding validation, severity-based prioritization, remediation, retesting support, and closure tracking. | Jawahar | Platform | Critical | Not Started | 2026-10-17 | 2026-11-02 |  | 0% | 100 | 0 |  | 11000 |  |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-050 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 08 | Build | Platform | Configuration Migration Tool Enhancement | Enhance the existing Configuration Migration Tool to improve automation, reliability, and control while moving configuration changes across environments and client deployments. This will reduce manual deployment effort, minimize migration errors, improve tenant/environment consistency, and support faster, more governed configuration rollouts. | MJ | Platform | High | Not Started | 2026-10-07 | 2026-11-15 |  | 0% | 240 | 0 |  | 26400 | T-049 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-051 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 09 | Hypercare | Reliability | Application Issue Fixes and Remediation | Issue Fixes - Analyse and fix application issues reported by delivery, internal, QA, or support teams outside planned feature implementation. This includes root cause analysis, required code/configuration fixes, validation, retesting support, and release through the planned delivery process. | Jawahar | Platform | Critical | Not Started | 2026-10-13 | 2026-12-21 |  | 0% | 420 | 0 |  | 46200 | T-050 |  | R-01 | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-052 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 10 | Hypercare | Reliability | GitLab DAST Enablement for Web Application and Admin Console | Enable DAST for all the deployable services - Enable GitLab DAST for the Web Application and Admin Console to perform runtime vulnerability scanning as part of the GitLab DevSecOps pipeline. This will help identify security issues in deployed application flows and improve release-level security validation | Jawahar | Platform | High | Not Started | 2026-10-12 | 2026-10-18 |  | 0% | 40 | 0 |  | 4400 | T-051 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-053 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 11 | Hypercare | Reliability | Release Management, Regression Testing and Test Automation | Release Management Activities - Regression Testing & Automation - Manage release activities, coordinate deployments, perform regression testing, maintain automation scripts, validate fixes, support release sign-off, and monitor post-release stability. This includes improving regression automation coverage to reduce manual effort and improve release quality. Note: Reduced this effort considering the release maangement will also go to the respective features, for the delivery customization this will be part of the delivery budget | Jawahar | Platform | Critical | Not Started | 2026-11-17 | 2026-12-11 |  | 0% | 150 | 0 |  | 16500 | T-052 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-054 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 12 | Hypercare | Reliability | Performance Testing, Tuning and Test Suite Management | Perform performance testing as per the planned test schedule, followed by performance fine-tuning, regression testing, test suite maintenance, fixture updates, and automation improvements. This includes adding or removing test fixtures, maintaining test scripts, validating performance improvements, and ensuring the test suite remains aligned with application changes. Note: Reduced this effort considering the release maangement will also go to the respective features | Jawahar | Platform | High | Not Started | 2026-10-27 | 2026-11-20 |  | 0% | 150 | 0 |  | 16500 | T-053 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-055 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 07 | Hypercare | Reliability | DevOps Management, Improvements and Pipeline Monitoring | Devops Management/Improvement/Monitoring - Manage and improve the existing DevOps setup by enhancing CI/CD pipelines, adding new deployment workflows, optimizing automation, monitoring pipeline health, troubleshooting deployment issues, and supporting DevOps changes required for new services, environments, and platform upgrades. | Jawahar | Platform | Critical | Not Started | 2026-10-22 | 2026-10-27 |  | 0% | 36 | 0 |  | 3960 | T-054 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-056 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 08 | Hypercare | Reliability | Release Based Feature Documentation | Create release based feature documentation covering new features, functional changes, configuration steps, usage flows, dependencies, screenshots, and known limitations. This will support delivery, QA, support, product, and implementation teams in understanding and adopting each release | Jawahar | Platform | Critical | Not Started | 2026-12-09 | 2026-12-14 |  | 0% | 36 | 0 |  | 3960 | T-055 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-057 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 09 | Hypercare | Reliability | Monthly Library Upgrade Assessment and Remediation Across Services | Perform monthly scheduled library and package upgrade assessment across 20+ services, including web apps, Node.js services, workers, and .NET services. This includes identifying available upgrades, assessing security and compatibility impact, handling breaking changes, applying required fixes, validating builds, and supporting regression/release readiness. | Jawahar | Platform | Critical | Not Started | 2026-10-03 | 2026-10-07 |  | 0% | 30 | 0 |  | 3300 | T-056 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-058 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 10 | Hypercare | Reliability | Cloud Usage Chargeback Model, Monthly Tenant-Level Allocation | Cloud Usage Charge back model (Monthly) - Prepare monthly tenant-level cloud usage chargeback by collecting cloud consumption data, applying agreed allocation rules, validating usage/cost anomalies, and publishing the monthly chargeback summary for each tenant. | Jawahar | Platform | Critical | Not Started | 2026-10-24 | 2026-10-28 |  | 0% | 12 | 0 |  | 1320 | T-057 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-059 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 11 | Hypercare | Reliability | Code Refactoring, Dependency Upgrades and Deprecated Code Removal | Improve code quality and maintainability by refactoring existing code, upgrading outdated dependencies, and removing deprecated or unused code/components. This helps reduce technical debt, improve system stability, support security compliance, and keep the application aligned with current technology standards. | Jawahar | Platform | High | Not Started | 2026-10-29 | 2026-12-07 |  | 0% | 240 | 0 |  | 26400 | T-058 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-060 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 12 | Build | Product Delivery | Table-Specific Metadata Model Storage Enhancement | Enhance the existing metadata model storage by separating the currently combined JSON structure into table-specific JSON structures. This will improve metadata maintainability, support table level configuration flexibility, reduce complexity, and make future schema or configuration changes easier to manage. | MJ | Platform | High | Not Started | 2026-11-28 | 2026-12-27 |  | 0% | 180 | 0 |  | 19800 | T-059 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-061 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 07 | Build | Product Delivery | System Wide AWS Redis Caching Layer Enablement | Extend the existing AWS Redis caching layer, currently used for fraud related processing, to support other time-consuming queries across the system. This will include identifying high-latency and frequently executed queries, defining suitable cache keys and expiry rules, implementing cache read/write logic, and validating performance improvements. The enhancement will help reduce database load, improve response time, and increase overall platform scalability. | MJ | Platform | High | Not Started | 2026-10-07 | 2026-11-02 |  | 0% | 160 | 0 |  | 17600 | T-060 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-062 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 08 | Build | Product Delivery | Workflow Engine Observability and Traceability Enhancements | Improve the Workflow Engine with better logging, monitoring, and traceability capabilities. This will help track workflow execution, identify failures faster, improve operational visibility, simplify troubleshooting, and strengthen overall engine reliability and supportability. | MJ | Platform | High | Not Started | 2026-11-26 | 2026-12-22 |  | 0% | 160 | 0 |  | 17600 | T-061 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-063 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 09 | Build | Product Delivery | Command and Query Engine Enhancement with GraphQL Evaluation | Enhance the Command and Query Engine by evaluating GraphQL-like querying capabilities and optimizing command/query handling. This will improve technical product capability by supporting more flexible data retrieval, better query control, optimized execution, and clearer separation between write operations and read operations. The activity will also include evaluating whether GraphQL is suitable for the platform based on performance, security, complexity, maintainability, and tenant-specific metadata requirements. | MJ | Platform | High | Not Started | 2026-11-08 | 2026-12-17 |  | 0% | 240 | 0 |  | 26400 | T-062 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-064 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 10 | Build | Product Delivery | Metadata Services Governance and Validation Enhancements | Enhance Metadata Services with improved sequence creation, schema validation, and governance controls. This will strengthen metadata platform capability by ensuring consistent metadata structures, reducing configuration errors, improving data/model integrity, and supporting better control over metadata-driven application behaviour | MJ | Platform | High | Not Started | 2026-10-04 | 2026-11-09 |  | 0% | 220 | 0 |  | 24200 | T-063 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-065 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 11 | Build | Platform | Connector Specific Property Model Enhancement | Enhance the connector module to support connector specific attached properties based on each connector’s behaviour and configuration needs. This will improve flexibility, reduce dependency on a fixed JSON structure, and make the connector framework more adaptable for different integration types. | MJ | Platform | High | Not Started | 2026-10-29 | 2026-11-24 |  | 0% | 160 | 0 |  | 17600 | T-064 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-066 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 12 | Hypercare | Reliability | Disaster Recovery Drill and Runbook Execution | Perform Disaster Recovery activity as per planned schedule - Perform the scheduled Disaster Recovery activity in the London region by executing the approved DR runbook, validating infrastructure, application, and data availability, coordinating failover/failback activities, documenting observations, and updating the runbook based on the exercise findings. | Jawahar | Platform | Critical | Not Started | 2026-11-05 | 2026-11-11 |  | 0% | 40 | 0 |  | 4400 | T-065 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-067 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 14 | Hypercare | Reliability | Application Issue Fixes and Remediation | Issue Fixes - Analyse and fix application issues reported by delivery, internal, QA, or support teams outside planned feature implementation. This includes root cause analysis, required code/configuration fixes, validation, retesting support, and release through the planned delivery process. | Jawahar | Platform | Critical | Not Started | 2027-01-18 | 2027-03-28 |  | 0% | 420 | 0 |  | 46200 |  |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-068 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 15 | Hypercare | Reliability | GitLab DAST Enablement for Web Application and Admin Console | Enable DAST for all the deployable services - Enable GitLab DAST for the Web Application and Admin Console to perform runtime vulnerability scanning as part of the GitLab DevSecOps pipeline. This will help identify security issues in deployed application flows and improve release-level security validation | Jawahar | Platform | High | Not Started | 2027-01-26 | 2027-02-01 |  | 0% | 40 | 0 |  | 4400 | T-067 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-069 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 16 | Hypercare | Reliability | Release Management, Regression Testing and Test Automation | Release Management Activities - Regression Testing & Automation - Manage release activities, coordinate deployments, perform regression testing, maintain automation scripts, validate fixes, support release sign-off, and monitor post-release stability. This includes improving regression automation coverage to reduce manual effort and improve release quality. Note: Reduced this effort considering the release maangement will also go to the respective features, for the delivery customization this will be part of the delivery budget | Jawahar | Platform | Critical | Not Started | 2027-01-13 | 2027-02-06 |  | 0% | 150 | 0 |  | 16500 | T-068 |  | R-15 | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-070 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 17 | Hypercare | Reliability | Performance Testing, Tuning and Test Suite Management | Perform performance testing as per the planned test schedule, followed by performance fine-tuning, regression testing, test suite maintenance, fixture updates, and automation improvements. This includes adding or removing test fixtures, maintaining test scripts, validating performance improvements, and ensuring the test suite remains aligned with application changes. Note: Reduced this effort considering the release maangement will also go to the respective features | Jawahar | Platform | High | Not Started | 2027-02-26 | 2027-03-22 |  | 0% | 150 | 0 |  | 16500 | T-069 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-071 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 18 | Hypercare | Reliability | DevOps Management, Improvements and Pipeline Monitoring | Devops Management/Improvement/Monitoring - Manage and improve the existing DevOps setup by enhancing CI/CD pipelines, adding new deployment workflows, optimizing automation, monitoring pipeline health, troubleshooting deployment issues, and supporting DevOps changes required for new services, environments, and platform upgrades. | Jawahar | Platform | Critical | Not Started | 2027-02-16 | 2027-02-21 |  | 0% | 36 | 0 |  | 3960 | T-070 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-072 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 13 | Hypercare | Reliability | Release Based Feature Documentation | Create release based feature documentation covering new features, functional changes, configuration steps, usage flows, dependencies, screenshots, and known limitations. This will support delivery, QA, support, product, and implementation teams in understanding and adopting each release | Jawahar | Platform | Critical | Not Started | 2027-02-12 | 2027-02-17 |  | 0% | 36 | 0 |  | 3960 | T-071 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-073 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 14 | Hypercare | Reliability | Monthly Library Upgrade Assessment and Remediation Across Services | Perform monthly scheduled library and package upgrade assessment across 20+ services, including web apps, Node.js services, workers, and .NET services. This includes identifying available upgrades, assessing security and compatibility impact, handling breaking changes, applying required fixes, validating builds, and supporting regression/release readiness. | Jawahar | Platform | Critical | Not Started | 2027-03-23 | 2027-03-27 |  | 0% | 30 | 0 |  | 3300 | T-072 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-074 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 15 | Hypercare | Reliability | Cloud Usage Chargeback Model, Monthly Tenant-Level Allocation | Cloud Usage Charge back model (Monthly) - Prepare monthly tenant-level cloud usage chargeback by collecting cloud consumption data, applying agreed allocation rules, validating usage/cost anomalies, and publishing the monthly chargeback summary for each tenant. | Jawahar | Platform | Critical | Not Started | 2027-03-06 | 2027-03-10 |  | 0% | 12 | 0 |  | 1320 | T-073 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-075 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 16 | Hypercare | Reliability | Yearly External VAPT for Web Application | Perform VAPT for web application as per planned schedule - Perform yearly external VAPT for the Web Application by coordinating with the external security team, providing required access and application details, reviewing reported findings, fixing applicable vulnerabilities, and supporting retesting and closure of identified issues. | Jawahar | Platform | Critical | Not Started | 2027-01-14 | 2027-02-19 |  | 0% | 220 | 0 |  | 24200 | T-074 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-076 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 17 | Hypercare | Reliability | Yearly External VAPT for Mobile Application | Perform VAPT for mobile application as per planned schedule - Perform yearly external VAPT for both iOS and Android mobile applications by coordinating with the external security team, sharing required app builds and test access, reviewing reported findings, fixing applicable vulnerabilities, and supporting retesting and closure of identified issues. | Jawahar | Platform | Critical | Not Started | 2027-02-20 | 2027-03-08 |  | 0% | 100 | 0 |  | 11000 | T-075 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-077 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 18 | Build | Platform | Form Builder Decoupling into Standalone NPM Package | Decouple the existing Form Builder from the Next.js codebase and convert it into a standalone reusable NPM package. This will improve modularity, enable reuse across multiple applications, reduce dependency on the main codebase, simplify maintenance, and support independent versioning and release management for Form Builder changes. | MJ | Platform | Medium | Not Started | 2027-01-25 | 2027-02-16 |  | 0% | 140 | 0 |  | 15400 | T-076 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=No ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-078 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 13 | Build | Product Delivery | View Builder Governance and Performance Enhancement | Enhance the existing View Builder to improve usability, performance, and governance. This includes introducing controls to manage excessive view creation, optimizing view execution, improving user experience, defining limits or approval rules where required, and reducing the risk of performance issues caused by unmanaged or duplicate user-created views. | MJ | Platform | Medium | Not Started | 2027-01-11 | 2027-02-26 |  | 0% | 280 | 0 |  | 30800 | T-077 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-079 | CS 2.0 Core — Tech Enhance | CS 2.0 Core | Tech Enhance | Sprint 14 | Build | Product Delivery | Application Health Monitoring Dashboard | Build an in-application health monitoring page to provide visibility into the status of key services outside Grafana. This will help product, support, and operations teams quickly monitor service availability, dependency health, API status, worker status, and critical system indicators directly from the application. | MJ | Platform | Medium | Not Started | 2027-01-01 | 2027-02-19 |  | 0% | 300 | 0 |  | 33000 | T-078 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=No ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-080 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 19 | Hypercare | Reliability | Application Issue Fixes and Remediation | Issue Fixes - Analyse and fix application issues reported by delivery, internal, QA, or support teams outside planned feature implementation. This includes root cause analysis, required code/configuration fixes, validation, retesting support, and release through the planned delivery process. | Jawahar | Platform | Critical | Not Started | 2027-04-12 | 2027-06-20 |  | 0% | 420 | 0 |  | 46200 |  |  |  | Confirm kickoff & acceptance criteria | R27.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q4 FY27 | No
T-081 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 20 | Hypercare | Reliability | GitLab DAST Enablement for Web Application and Admin Console | Enable DAST for all the deployable services - Enable GitLab DAST for the Web Application and Admin Console to perform runtime vulnerability scanning as part of the GitLab DevSecOps pipeline. This will help identify security issues in deployed application flows and improve release-level security validation | Jawahar | Platform | High | Not Started | 2027-05-01 | 2027-05-07 |  | 0% | 40 | 0 |  | 4400 | T-080 |  |  | Confirm kickoff & acceptance criteria | R27.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q4 FY27 | No
T-082 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 21 | Hypercare | Reliability | Release Management, Regression Testing and Test Automation | Release Management Activities - Regression Testing & Automation - Manage release activities, coordinate deployments, perform regression testing, maintain automation scripts, validate fixes, support release sign-off, and monitor post-release stability. This includes improving regression automation coverage to reduce manual effort and improve release quality. Note: Reduced this effort considering the release maangement will also go to the respective features, for the delivery customization this will be part of the delivery budget | Jawahar | Platform | Critical | Not Started | 2027-04-26 | 2027-05-20 |  | 0% | 150 | 0 |  | 16500 | T-081 |  |  | Confirm kickoff & acceptance criteria | R27.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q4 FY27 | No
T-083 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 22 | Hypercare | Reliability | Performance Testing, Tuning and Test Suite Management | Perform performance testing as per the planned test schedule, followed by performance fine-tuning, regression testing, test suite maintenance, fixture updates, and automation improvements. This includes adding or removing test fixtures, maintaining test scripts, validating performance improvements, and ensuring the test suite remains aligned with application changes. Note: Reduced this effort considering the release maangement will also go to the respective features | Jawahar | Platform | High | Not Started | 2027-05-12 | 2027-06-05 |  | 0% | 150 | 0 |  | 16500 | T-082 |  |  | Confirm kickoff & acceptance criteria | R27.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q4 FY27 | No
T-084 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 23 | Hypercare | Reliability | DevOps Management, Improvements and Pipeline Monitoring | Devops Management/Improvement/Monitoring - Manage and improve the existing DevOps setup by enhancing CI/CD pipelines, adding new deployment workflows, optimizing automation, monitoring pipeline health, troubleshooting deployment issues, and supporting DevOps changes required for new services, environments, and platform upgrades. | Jawahar | Platform | Critical | Not Started | 2027-05-19 | 2027-05-24 |  | 0% | 36 | 0 |  | 3960 | T-083 |  | R-14 | Confirm kickoff & acceptance criteria | R27.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q4 FY27 | No
T-085 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 24 | Hypercare | Reliability | Release Based Feature Documentation | Create release based feature documentation covering new features, functional changes, configuration steps, usage flows, dependencies, screenshots, and known limitations. This will support delivery, QA, support, product, and implementation teams in understanding and adopting each release | Jawahar | Platform | Critical | Not Started | 2027-05-31 | 2027-06-05 |  | 0% | 36 | 0 |  | 3960 | T-084 |  |  | Confirm kickoff & acceptance criteria | R27.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q4 FY27 | No
T-086 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 19 | Hypercare | Reliability | Monthly Library Upgrade Assessment and Remediation Across Services | Perform monthly scheduled library and package upgrade assessment across 20+ services, including web apps, Node.js services, workers, and .NET services. This includes identifying available upgrades, assessing security and compatibility impact, handling breaking changes, applying required fixes, validating builds, and supporting regression/release readiness. | Jawahar | Platform | Critical | Not Started | 2027-05-14 | 2027-05-18 |  | 0% | 30 | 0 |  | 3300 | T-085 |  |  | Confirm kickoff & acceptance criteria | R27.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q4 FY27 | No
T-087 | CS 2.0 Core — Tech Maintenance | CS 2.0 Core | Tech Maintenance | Sprint 20 | Hypercare | Reliability | Cloud Usage Chargeback Model, Monthly Tenant-Level Allocation | Cloud Usage Charge back model (Monthly) - Prepare monthly tenant-level cloud usage chargeback by collecting cloud consumption data, applying agreed allocation rules, validating usage/cost anomalies, and publishing the monthly chargeback summary for each tenant. | Jawahar | Platform | Critical | Not Started | 2027-04-09 | 2027-04-13 |  | 0% | 12 | 0 |  | 1320 | T-086 |  |  | Confirm kickoff & acceptance criteria | R27.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q4 FY27 | No
T-088 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 03 | Build | Data | Insight Agent Requirements Building and POC Closure |  | Siva | Data & AI | High | Not Started | 2026-08-01 | 2026-08-17 |  | 0% | 100 | 0 |  | 11000 |  |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-089 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 04 | Build | Data | Insights Agent | Phase 1 - ANSWER & GUIDE | Siva | Data & AI | High | Not Started | 2026-08-07 | 2026-09-08 |  | 0% | 200 | 0 |  | 22000 | T-088 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-090 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 05 | Build | Data | Insights Agent | Phase 2 - EXPLAIN & DIAGNOSE | Siva | Data & AI | High | In Progress | 2026-08-25 | 2026-09-26 |  | 35% | 200 | 72.8 |  | 22000 | T-089 |  |  | Continue sprint commitments; demos Friday | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-091 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 06 | Build | Data | Insights Agent | Phase 3 - PREDICT & OPTIMISE | Siva | Data & AI | High | Not Started | 2026-07-04 | 2026-08-05 |  | 0% | 200 | 0 |  | 22000 | T-090 |  |  | Confirm kickoff & acceptance criteria | R26.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-092 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 07 | Build | Data | Insights Agent | Phase 1 - ANSWER & GUIDE | Siva | Data & AI | High | Not Started | 2026-11-01 | 2026-12-03 |  | 0% | 200 | 0 |  | 22000 | T-091 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-093 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 08 | Build | Data | Insights Agent | Phase 2 - EXPLAIN & DIAGNOSE | Siva | Data & AI | High | Not Started | 2026-11-04 | 2026-12-06 |  | 0% | 200 | 0 |  | 22000 | T-092 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-094 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 09 | Build | Data | Insights Agent | Phase 3 - PREDICT & OPTIMISE | Siva | Data & AI | High | Not Started | 2026-10-06 | 2026-11-07 |  | 0% | 200 | 0 |  | 22000 | T-093 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-095 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 10 | Build | Data | Journey Builder - Requirements Building | Journey Builder Requirements. Build the work package, Design and estimate based on the work package | Siva | Data & AI | High | Not Started | 2026-11-27 | 2026-12-13 |  | 0% | 100 | 0 |  | 11000 | T-094 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-096 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 11 | Build | Data | Journey Builder | Phase 1 - ORCHESTRATE - Build the Engine Low-code journey canvas with drag-and-drop trigger, wait, and condition logic. Automated actions across communication, incentives, and learning interventions. Omni-channel response tracking with automated follow-up sequencing. Extend journeys with Agent Node that invoke specialised AI agents for contextual decisioning and message personalization. | Siva | Data & AI | High | Not Started | 2026-10-07 | 2026-11-08 |  | 0% | 200 | 0 |  | 22000 | T-095 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-097 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 12 | Build | Data | Journey Builder | Phase 2 - GUIDE with Recommendations Journey Builder framework powers Earn Advisor to continuously guide partners towards the highest-value earning actions. A Next-Best-Action Agent evaluates partner context across sales patterns, behaviours and program participation signals. Identifies and ranks high-value opportunities - including product mix gaps, cross-sell opportunities and time-sensitive incentives. Agent presents prioritised actions back to Journey Builder to enable contextual interventions. | Siva | Data & AI | High | Not Started | 2026-11-12 | 2026-12-14 |  | 0% | 200 | 0 |  | 22000 | T-096 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-098 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 07 | Build | Data | Journey Builder | Phase 3 - PREDICT with Intelligence Build prediction agents that continuously analyse participant context across partner performance, behaviours and engagement patterns. Generate explainable outcome predictions - such as churn risk, activation likelihood, target shortfalls and tier progression risk. Return prediction confidence, key drivers & recommended interventions rather than standalone scores. Present predicted outcomes to Journey Builder to enable contextual interventions. | Siva | Data & AI | High | Not Started | 2026-11-17 | 2026-12-19 |  | 0% | 200 | 0 |  | 22000 | T-097 |  |  | Confirm kickoff & acceptance criteria | R26.Q2 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q2 FY27 | No
T-099 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 15 | Build | Data | Journey Builder | Phase 1 - ORCHESTRATE - Build the Engine Low-code journey canvas with drag-and-drop trigger, wait, and condition logic. Automated actions across communication, incentives, and learning interventions. Omni-channel response tracking with automated follow-up sequencing. Extend journeys with Agent Node that invoke specialised AI agents for contextual decisioning and message personalization. | Siva | Data & AI | High | Not Started | 2027-01-09 | 2027-02-10 |  | 0% | 200 | 0 |  | 22000 | T-098 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-100 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 16 | Build | Data | Journey Builder | Phase 2 - GUIDE with Recommendations Journey Builder framework powers Earn Advisor to continuously guide partners towards the highest-value earning actions. A Next-Best-Action Agent evaluates partner context across sales patterns, behaviours and program participation signals. Identifies and ranks high-value opportunities - including product mix gaps, cross-sell opportunities and time-sensitive incentives. Agent presents prioritised actions back to Journey Builder to enable contextual interventions. | Siva | Data & AI | High | Not Started | 2027-01-20 | 2027-02-21 |  | 0% | 200 | 0 |  | 22000 | T-099 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-101 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 17 | Build | Data | Journey Builder | Phase 3 - PREDICT with Intelligence Build prediction agents that continuously analyse participant context across partner performance, behaviours and engagement patterns. Generate explainable outcome predictions - such as churn risk, activation likelihood, target shortfalls and tier progression risk. Return prediction confidence, key drivers & recommended interventions rather than standalone scores. Present predicted outcomes to Journey Builder to enable contextual interventions. | Siva | Data & AI | High | Not Started | 2027-02-12 | 2027-03-16 |  | 0% | 200 | 0 |  | 22000 | T-100 |  |  | Confirm kickoff & acceptance criteria | R27.Q1 | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=Q3 FY27 | No
T-102 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 25 | Build | Data | AI-Powered Journey Intelligence Platform | Build AI agents, predictive models, and intelligence datasets that power personalized recommendations, next-best actions, engagement insights, and behavioral analytics across partner journeys. | Siva | Data & AI | High | Not Started | 2027-05-30 | 2027-06-26 |  | 0% | 40 | 0 |  | 4400 | T-101 |  |  | Confirm kickoff & acceptance criteria | N/A | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-103 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 26 | Build | Data | Data & Intelligence Foundation Modernization | Establish a unified intelligence platform integrating behavioral, communication, marketplace, and web analytics data to support AI, reporting, and decision intelligence. | Siva | Data & AI | High | Not Started | 2027-06-07 | 2027-06-27 |  | 0% | 40 | 0 |  | 4400 | T-102 |  |  | Confirm kickoff & acceptance criteria | N/A | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-104 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 26 | Build | Data | Promotion Optimization & Decision Intelligence | Deliver promotion simulation, ROI forecasting, budget optimization, and data-driven program management capabilities to improve campaign effectiveness and business outcomes. | Siva | Data & AI | High | Not Started | 2027-05-24 | 2027-06-20 |  | 0% | 40 | 0 |  | 4400 | T-103 |  |  | Confirm kickoff & acceptance criteria | N/A | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-105 | CS 2.0 Data — PIS New Feature | CS 2.0 Data | PIS New Feature | Sprint 22 | Build | Data | Partner Intelligence & Fraud Analytics Suite | Enhance Partner360 and Program360 with predictive insights, opportunity intelligence, advanced fraud detection, anomaly monitoring, and adaptive risk scoring. | Siva | Data & AI | High | Not Started | 2027-04-09 | 2027-04-29 |  | 0% | 40 | 0 |  | 4400 | T-104 |  |  | Confirm kickoff & acceptance criteria | N/A | Include=Yes ¦ Source=FY27 V1 ¦ Timeline=TBD FY27 ¦ Hours=TBD in source | No
T-106 | Unassigned — Tech Maintenance | Unassigned | Tech Maintenance | Sprint 01 | Hypercare | Reliability | Update Tuskr Connector and Remove duplicate | Remove the duplicate test cases. With new tuskr api, update the tuskr connector to accept external id and create a provision for updating the test case. Migrate the existing test cases to have the external id | Kadarkarai | Core Product | Critical | At Risk | 2026-09-02 | 2026-09-06 |  | 16% | 18 | 2.8 |  | 1980 |  |  | R-13 | Clarify Include/Pending decision; rebaseline if needed | R26.Q1 | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | Yes
T-107 | Unassigned — Tech Maintenance | Unassigned | Tech Maintenance | Sprint 02 | Hypercare | Reliability | Mobile Automation POC | Find and confirm on the Mobile automation and come up with the POC | Kadarkarai | Core Product | High | Blocked | 2026-08-31 | 2026-09-06 |  | 14% | 42 | 5.9 |  | 4620 | T-106 | T-106 | R-11 | Resolve blocker with dependency owner | R26.Q1 | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-108 | Unassigned — Tech Maintenance | Unassigned | Tech Maintenance | Sprint 03 | Hypercare | Reliability | Automating the main features for mobile | Completing the mobile Automation for the basic features including login, self registration, invoice claim, coupon claim, verify invoice claim history, verify coupon claim history, Verify the profile page | Kadarkarai | Core Product | High | Blocked | 2026-07-25 | 2026-08-20 |  | 15% | 160 | 24 |  | 17600 | T-107 | T-107 | R-14 | Resolve blocker with dependency owner | R26.Q1 | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No
T-109 | Unassigned — Tech Maintenance | Unassigned | Tech Maintenance | Sprint 04 | Hypercare | Reliability | Audit Findings remediation |  | Kadarkarai | Core Product | High | At Risk | 2026-07-29 | 2026-08-02 |  | 21% | 18 | 4 |  | 1980 | T-108 |  | R-14 | Clarify Include/Pending decision; rebaseline if needed | R26.Q1 | Include=Pending ¦ Source=FY27 V1 ¦ Timeline=Q1 FY27 | No

## Gantt Chart
GANTT CHART — FY27 (Weekly / Monthly / Quarterly)
Bars auto-highlight from Start/End. Legend: Green=Completed · Blue=In Progress · Yellow=At Risk · Red=Blocked/Critical · Grey=Not Started · ◆=Milestone week · Orange header=Current week
Task ID | Task Name | Owner | Status | Start | End | % Complete | Critical | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28
T-001 | Shutting down BRIKS service from Nackle | MJ | At Risk | 2026-09-22 | 2026-09-28 | 13% | No
T-002 | Shutting Down Coupon/OTP Services | MJ | In Progress | 2026-07-10 | 2026-07-23 | 36% | No
T-003 | Integrate the email validation service for Channel Smart 1.0(Roshni to check) | MJ | In Progress | 2026-08-02 | 2026-08-08 | 36% | No
T-004 | Build Unsubscribe feature for all the promotional emails(Roshni to check) | MJ | Not Started | 2026-08-01 | 2026-08-10 | 0% | No
T-005 | Cash + Wallet + Compliance - Integration patch for CS 1.0 | MJ | Not Started | 2026-08-01 | 2026-09-02 | 0% | No
T-006 | Build Pipeline for Achievo to be updated | MJ | Not Started | 2026-09-17 | 2026-09-26 | 0% | No
T-007 | Integrate the email validation service for Channel Smart 2.0(Roshni to check) | MJ | Not Started | 2026-08-23 | 2026-08-29 | 0% | No
T-008 | Build Unsubscribe feature for all the promotional emails(Roshni to check) | MJ | Not Started | 2026-08-26 | 2026-09-04 | 0% | No
T-009 | ERP Connerctor Service(Saleforce) | MJ | Not Started | 2026-07-01 | 2026-08-27 | 0% | No
T-010 | Technology refresh | Jawahar | In Progress | 2026-08-31 | 2026-09-12 | 29% | No
T-011 | Fix for Critical Performance Issue(Claims, File Upload) | Jawahar | In Progress | 2026-09-06 | 2026-09-19 | 22% | No
T-012 | Build a game engine - Requirements | MJ | Not Started | 2026-07-05 | 2026-07-14 | 0% | No
T-013 | BRD Composer | MJ | In Progress | 2026-08-03 | 2026-09-21 | 24% | No
T-014 | Communication connector which can support the Whatsapp and Wechat communicaton bi direction | MJ | Not Started | 2026-07-09 | 2026-09-16 | 0% | No
T-015 | AI-Powered Claim Validation | MJ | Not Started | 2027-01-23 | 2027-02-01 | 0% | No
T-016 | MDF Budget Management & Incentivization | MJ | At Risk | 2027-05-28 | 2027-06-06 | 9% | No
T-017 | AI Display Audit & Compliance Management | MJ | Blocked | 2027-04-05 | 2027-05-02 | 14% | No
T-018 | Organization-Centric Loyalty Journey | MJ | At Risk | 2027-04-23 | 2027-05-20 | 5% | No
T-019 | Social Advocacy & Partner Influence Platform | MJ | At Risk | 2027-04-23 | 2027-05-13 | 20% | No
T-020 | Partner Referral & Growth Engine | MJ | At Risk | 2027-06-06 | 2027-06-15 | 12% | No
T-021 | AI-Powered Audience Segmentation | MJ | At Risk | 2027-05-06 | 2027-06-02 | 7% | No
T-022 | Embedded Gamification Experiences | MJ | At Risk | 2027-05-21 | 2027-05-30 | 15% | No
T-023 | Achievo - UI/UX Improvements | Shriguru | Not Started | 2026-08-02 | 2026-08-22 | 0% | No
T-024 | Achievo - Mobile Performance Improvement.(Analysis) | Shriguru | In Progress | 2026-07-11 | 2026-07-15 | 29% | Yes
T-025 | Achievo - Mobile Performance Improvement.(Implementation) | Shriguru | In Progress | 2026-09-13 | 2026-09-22 | 24% | Yes
T-026 | Achievo - Android 16 Upgrade | Shriguru | Not Started | 2026-08-31 | 2026-09-06 | 0% | No
T-027 | Achievo - iOS Updates | Shriguru | In Progress | 2026-07-16 | 2026-07-22 | 11% | No
T-028 | Achievo Mobile Experience Modernization | Shriguru | At Risk | 2027-05-08 | 2027-05-21 | 24% | No
T-029 | Existing Product Backlog and Delivery Priority Items as needed to be added to Core Product | MJ | Blocked | 2027-06-11 | 2027-06-20 | 15% | No
T-030 | New UI for platform portal | MJ | Not Started | 2026-08-28 | 2026-09-23 | 0% | No
T-031 | Architecture Proposal: Core + Extension Model for Participant Portals | MJ | Not Started | 2026-07-06 | 2026-09-13 | 0% | No
T-032 | File Upload Module Stabilization and Validation Enhancements (Check if it can be moved to Q2) | MJ | Not Started | 2026-07-12 | 2026-09-19 | 0% | No
T-033 | Release Governance, Code Merge and Deployment Control | Jawahar | In Progress | 2026-08-09 | 2026-09-14 | 22% | No
T-034 | Achievo Mobile App Upgrades and Store Policy Compliance Updates | Jawahar | Not Started | 2026-07-22 | 2026-09-12 | 0% | No
T-035 | Next.js 16.x LTS Upgrade for Admin Console and Platform Web Apps | Jawahar | Not Started | 2026-08-22 | 2026-09-27 | 0% | No
T-036 | Scalable File Upload Processing Enhancement | MJ | Not Started | 2026-07-23 | 2026-08-21 | 0% | No
T-037 | AWS Secrets Manager Enforcement for Service Credentials | MJ | In Progress | 2026-07-06 | 2026-08-01 | 42% | Yes
T-038 | SAST Vulnerability Fixes Based on GitLab Security Findings | Jawahar | In Progress | 2026-07-30 | 2026-08-18 | 29% | Yes
T-039 | Kubernetes Resource Optimization | Jawahar | In Progress | 2026-08-31 | 2026-09-19 | 34% | Yes
T-040 | Infrastructure and Application Monitoring for EKS Platform | Jawahar | In Progress | 2026-08-05 | 2026-08-20 | 30% | Yes
T-041 | Application Issue Fixes and Remediation | Jawahar | In Progress | 2026-07-18 | 2026-09-25 | 41% | Yes
T-042 | GitLab DAST Enablement for Web Application and Admin Console | Jawahar | Not Started | 2026-08-08 | 2026-08-14 | 0% | No
T-043 | Release Management, Regression Testing and Test Automation | Kadarkarai | Not Started | 2026-09-04 | 2026-09-28 | 0% | No
T-044 | Performance Testing, Tuning and Test Suite Management | Kadarkarai | Not Started | 2026-07-20 | 2026-08-13 | 0% | No
T-045 | DevOps Management, Improvements and Pipeline Monitoring | Jawahar | Not Started | 2026-08-12 | 2026-08-17 | 0% | No
T-046 | Release Based Feature Documentation | Jawahar | Not Started | 2026-07-08 | 2026-07-13 | 0% | No
T-047 | Monthly Library Upgrade Assessment and Remediation Across Services | Jawahar | In Progress | 2026-07-16 | 2026-07-20 | 34% | Yes
T-048 | Cloud Usage Chargeback Model, Monthly Tenant-Level Allocation | Jawahar | In Progress | 2026-07-11 | 2026-07-15 | 25% | Yes
T-049 | Internal VAPT - Half-Yearly Penetration Testing and Fixes | Jawahar | Not Started | 2026-10-17 | 2026-11-02 | 0% | No
T-050 | Configuration Migration Tool Enhancement | MJ | Not Started | 2026-10-07 | 2026-11-15 | 0% | No
T-051 | Application Issue Fixes and Remediation | Jawahar | Not Started | 2026-10-13 | 2026-12-21 | 0% | No
T-052 | GitLab DAST Enablement for Web Application and Admin Console | Jawahar | Not Started | 2026-10-12 | 2026-10-18 | 0% | No
T-053 | Release Management, Regression Testing and Test Automation | Jawahar | Not Started | 2026-11-17 | 2026-12-11 | 0% | No
T-054 | Performance Testing, Tuning and Test Suite Management | Jawahar | Not Started | 2026-10-27 | 2026-11-20 | 0% | No
T-055 | DevOps Management, Improvements and Pipeline Monitoring | Jawahar | Not Started | 2026-10-22 | 2026-10-27 | 0% | No
T-056 | Release Based Feature Documentation | Jawahar | Not Started | 2026-12-09 | 2026-12-14 | 0% | No
T-057 | Monthly Library Upgrade Assessment and Remediation Across Services | Jawahar | Not Started | 2026-10-03 | 2026-10-07 | 0% | No
T-058 | Cloud Usage Chargeback Model, Monthly Tenant-Level Allocation | Jawahar | Not Started | 2026-10-24 | 2026-10-28 | 0% | No
T-059 | Code Refactoring, Dependency Upgrades and Deprecated Code Removal | Jawahar | Not Started | 2026-10-29 | 2026-12-07 | 0% | No
T-060 | Table-Specific Metadata Model Storage Enhancement | MJ | Not Started | 2026-11-28 | 2026-12-27 | 0% | No
T-061 | System Wide AWS Redis Caching Layer Enablement | MJ | Not Started | 2026-10-07 | 2026-11-02 | 0% | No
T-062 | Workflow Engine Observability and Traceability Enhancements | MJ | Not Started | 2026-11-26 | 2026-12-22 | 0% | No
T-063 | Command and Query Engine Enhancement with GraphQL Evaluation | MJ | Not Started | 2026-11-08 | 2026-12-17 | 0% | No
T-064 | Metadata Services Governance and Validation Enhancements | MJ | Not Started | 2026-10-04 | 2026-11-09 | 0% | No
T-065 | Connector Specific Property Model Enhancement | MJ | Not Started | 2026-10-29 | 2026-11-24 | 0% | No
T-066 | Disaster Recovery Drill and Runbook Execution | Jawahar | Not Started | 2026-11-05 | 2026-11-11 | 0% | No
T-067 | Application Issue Fixes and Remediation | Jawahar | Not Started | 2027-01-18 | 2027-03-28 | 0% | No
T-068 | GitLab DAST Enablement for Web Application and Admin Console | Jawahar | Not Started | 2027-01-26 | 2027-02-01 | 0% | No
T-069 | Release Management, Regression Testing and Test Automation | Jawahar | Not Started | 2027-01-13 | 2027-02-06 | 0% | No
T-070 | Performance Testing, Tuning and Test Suite Management | Jawahar | Not Started | 2027-02-26 | 2027-03-22 | 0% | No
T-071 | DevOps Management, Improvements and Pipeline Monitoring | Jawahar | Not Started | 2027-02-16 | 2027-02-21 | 0% | No
T-072 | Release Based Feature Documentation | Jawahar | Not Started | 2027-02-12 | 2027-02-17 | 0% | No
T-073 | Monthly Library Upgrade Assessment and Remediation Across Services | Jawahar | Not Started | 2027-03-23 | 2027-03-27 | 0% | No
T-074 | Cloud Usage Chargeback Model, Monthly Tenant-Level Allocation | Jawahar | Not Started | 2027-03-06 | 2027-03-10 | 0% | No
T-075 | Yearly External VAPT for Web Application | Jawahar | Not Started | 2027-01-14 | 2027-02-19 | 0% | No
T-076 | Yearly External VAPT for Mobile Application | Jawahar | Not Started | 2027-02-20 | 2027-03-08 | 0% | No
T-077 | Form Builder Decoupling into Standalone NPM Package | MJ | Not Started | 2027-01-25 | 2027-02-16 | 0% | No
T-078 | View Builder Governance and Performance Enhancement | MJ | Not Started | 2027-01-11 | 2027-02-26 | 0% | No
T-079 | Application Health Monitoring Dashboard | MJ | Not Started | 2027-01-01 | 2027-02-19 | 0% | No
T-080 | Application Issue Fixes and Remediation | Jawahar | Not Started | 2027-04-12 | 2027-06-20 | 0% | No
T-081 | GitLab DAST Enablement for Web Application and Admin Console | Jawahar | Not Started | 2027-05-01 | 2027-05-07 | 0% | No
T-082 | Release Management, Regression Testing and Test Automation | Jawahar | Not Started | 2027-04-26 | 2027-05-20 | 0% | No
T-083 | Performance Testing, Tuning and Test Suite Management | Jawahar | Not Started | 2027-05-12 | 2027-06-05 | 0% | No
T-084 | DevOps Management, Improvements and Pipeline Monitoring | Jawahar | Not Started | 2027-05-19 | 2027-05-24 | 0% | No
T-085 | Release Based Feature Documentation | Jawahar | Not Started | 2027-05-31 | 2027-06-05 | 0% | No
T-086 | Monthly Library Upgrade Assessment and Remediation Across Services | Jawahar | Not Started | 2027-05-14 | 2027-05-18 | 0% | No
T-087 | Cloud Usage Chargeback Model, Monthly Tenant-Level Allocation | Jawahar | Not Started | 2027-04-09 | 2027-04-13 | 0% | No
T-088 | Insight Agent Requirements Building and POC Closure | Siva | Not Started | 2026-08-01 | 2026-08-17 | 0% | No
T-089 | Insights Agent | Siva | Not Started | 2026-08-07 | 2026-09-08 | 0% | No
T-090 | Insights Agent | Siva | In Progress | 2026-08-25 | 2026-09-26 | 35% | No
T-091 | Insights Agent | Siva | Not Started | 2026-07-04 | 2026-08-05 | 0% | No
T-092 | Insights Agent | Siva | Not Started | 2026-11-01 | 2026-12-03 | 0% | No
T-093 | Insights Agent | Siva | Not Started | 2026-11-04 | 2026-12-06 | 0% | No
T-094 | Insights Agent | Siva | Not Started | 2026-10-06 | 2026-11-07 | 0% | No
T-095 | Journey Builder - Requirements Building | Siva | Not Started | 2026-11-27 | 2026-12-13 | 0% | No
T-096 | Journey Builder | Siva | Not Started | 2026-10-07 | 2026-11-08 | 0% | No
T-097 | Journey Builder | Siva | Not Started | 2026-11-12 | 2026-12-14 | 0% | No
T-098 | Journey Builder | Siva | Not Started | 2026-11-17 | 2026-12-19 | 0% | No
T-099 | Journey Builder | Siva | Not Started | 2027-01-09 | 2027-02-10 | 0% | No
T-100 | Journey Builder | Siva | Not Started | 2027-01-20 | 2027-02-21 | 0% | No
T-101 | Journey Builder | Siva | Not Started | 2027-02-12 | 2027-03-16 | 0% | No
T-102 | AI-Powered Journey Intelligence Platform | Siva | Not Started | 2027-05-30 | 2027-06-26 | 0% | No
T-103 | Data & Intelligence Foundation Modernization | Siva | Not Started | 2027-06-07 | 2027-06-27 | 0% | No
T-104 | Promotion Optimization & Decision Intelligence | Siva | Not Started | 2027-05-24 | 2027-06-20 | 0% | No
T-105 | Partner Intelligence & Fraud Analytics Suite | Siva | Not Started | 2027-04-09 | 2027-04-29 | 0% | No
T-106 | Update Tuskr Connector and Remove duplicate | Kadarkarai | At Risk | 2026-09-02 | 2026-09-06 | 16% | Yes
T-107 | Mobile Automation POC | Kadarkarai | Blocked | 2026-08-31 | 2026-09-06 | 14% | No
T-108 | Automating the main features for mobile | Kadarkarai | Blocked | 2026-07-25 | 2026-08-20 | 15% | No
T-109 | Audit Findings remediation | Kadarkarai | At Risk | 2026-07-29 | 2026-08-02 | 21% | No
MONTHLY VIEW — Task count active per month (formula)
Month | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01
QUARTERLY VIEW — Active tasks by quarter
| FY27-Q1 | FY27-Q2 | FY27-Q3 | FY27-Q4
Start | 2026-07-01 | 2026-10-01 | 2027-01-01 | 2027-04-01
End | 2026-09-30 | 2026-12-31 | 2027-03-31 | 2027-06-30
Active Tasks

## Resource Planning
RESOURCE PLANNING — CAPACITY & UTILIZATION
Allocated Hours roll up from Project Tracker by Owner. Utilization & Overallocation are formula-driven.
Resource | Role | Capacity (h) | Allocated Hours | Remaining Hours | Utilization % | Vacation (h) | Leave (h) | Overallocated?
Jawahar | Tech Lead — Platform / Core | 5900 |  |  |  | 80 | 24
Kadarkarai | Engineer — Platform | 1200 |  |  |  | 40 | 24
MJ | EM / Tech Lead — CS | 6850 |  |  |  | 80 | 24
Shriguru | Engineer — Achievo / Rewards | 1200 |  |  |  | 40 | 24
Siva | Tech Lead — Data / PIS | 3150 |  |  |  | 80 | 24
MONTHLY ALLOCATION (Planned Hours by Owner × Month)
Resource | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01
Jawahar
Kadarkarai
MJ
Shriguru
Siva
QUARTER-WISE UTILIZATION %
Resource | FY27-Q1 | FY27-Q2 | FY27-Q3 | FY27-Q4
Jawahar
Kadarkarai
MJ
Shriguru
Siva
Formulas:
Role = SUMPRODUCT(('Project Tracker'!$J5:J113=[Resource])*('Project Tracker'!$N5:N113<=EOMONTH(B13,0))*('Project Tracker'!$O5:O113>=B13)*('Project Tracker'!$R5:R113))
Capacity (h) = SUMPRODUCT(('Project Tracker'!$J5:J113=[Resource])*('Project Tracker'!$N5:N113<=EOMONTH(C13,0))*('Project Tracker'!$O5:O113>=C13)*('Project Tracker'!$R5:R113))
Allocated Hours = SUMPRODUCT(('Project Tracker'!$J5:J113=[Resource])*('Project Tracker'!$N5:N113<=EOMONTH(D13,0))*('Project Tracker'!$O5:O113>=D13)*('Project Tracker'!$R5:R113))
Remaining Hours = SUMPRODUCT(('Project Tracker'!$J5:J113=[Resource])*('Project Tracker'!$N5:N113<=EOMONTH(E13,0))*('Project Tracker'!$O5:O113>=E13)*('Project Tracker'!$R5:R113))
Utilization % = SUMPRODUCT(('Project Tracker'!$J5:J113=[Resource])*('Project Tracker'!$N5:N113<=EOMONTH(F13,0))*('Project Tracker'!$O5:O113>=F13)*('Project Tracker'!$R5:R113))
Vacation (h) = SUMPRODUCT(('Project Tracker'!$J5:J113=[Resource])*('Project Tracker'!$N5:N113<=EOMONTH(G13,0))*('Project Tracker'!$O5:O113>=G13)*('Project Tracker'!$R5:R113))
Leave (h) = SUMPRODUCT(('Project Tracker'!$J5:J113=[Resource])*('Project Tracker'!$N5:N113<=EOMONTH(H13,0))*('Project Tracker'!$O5:O113>=H13)*('Project Tracker'!$R5:R113))
Overallocated? = SUMPRODUCT(('Project Tracker'!$J5:J113=[Resource])*('Project Tracker'!$N5:N113<=EOMONTH(I13,0))*('Project Tracker'!$O5:O113>=I13)*('Project Tracker'!$R5:R113))

## Milestones
MILESTONES — FY27 GOVERNANCE
Delay and 'Upcoming within 14 days' are formula-driven.
Milestone ID | Milestone | Owner | Planned Date | Actual Date | Status | Delay (days) | Upcoming within 14 days
M-01 | FY27 Planning Baseline Locked (FY27 V1) | Jawahar | 2026-07-10 | 2026-07-08 | Completed
M-02 | Q1 Governance Checkpoint | Kadarkarai | 2026-09-25 |  | Not Started
M-03 | Q2 Governance Checkpoint | MJ | 2026-12-18 |  | Not Started
M-04 | Q3 Governance Checkpoint | Shriguru | 2027-03-20 |  | Not Started
M-05 | Q4 / FY27 Closeout | Siva | 2027-06-30 |  | Not Started
M-06 | CS 1.0 — Q1 exit gate | Jawahar | 2026-09-30 |  | In Progress
M-07 | CS 1.0 — H1 checkpoint | Kadarkarai | 2026-12-31 |  | Not Started
M-08 | CS 2.0 — Q1 exit gate | MJ | 2026-09-30 |  | In Progress
M-09 | CS 2.0 — H1 checkpoint | Shriguru | 2026-12-31 |  | Not Started
M-10 | CS 2.0 Achievo — Q1 exit gate | Siva | 2026-09-30 |  | In Progress
M-11 | CS 2.0 Achievo — H1 checkpoint | Jawahar | 2026-12-31 |  | Not Started
M-12 | CS 2.0 Core — Q1 exit gate | Kadarkarai | 2026-09-30 |  | In Progress
M-13 | CS 2.0 Core — H1 checkpoint | MJ | 2026-12-31 |  | Not Started
M-14 | CS 2.0 Data — Q1 exit gate | Shriguru | 2026-09-30 |  | In Progress
M-15 | CS 2.0 Data — H1 checkpoint | Siva | 2026-12-31 |  | Not Started
M-16 | Unassigned — Q1 exit gate | Jawahar | 2026-09-30 |  | Not Started
M-17 | Unassigned — H1 checkpoint | Kadarkarai | 2026-12-31 |  | Not Started
M-18 | Critical: Achievo - UI/UX Improvements | MJ | 2026-08-22 |  | Not Started
M-19 | Critical: Achievo - Mobile Performance Improvement.(Analysis) | Shriguru | 2026-07-15 |  | In Progress
M-20 | Critical: Achievo - Mobile Performance Improvement.(Implementation) | Siva | 2026-09-22 |  | In Progress
M-21 | Critical: Architecture Proposal: Core + Extension Model for Participan | Jawahar | 2026-09-13 |  | Not Started
M-22 | Critical: File Upload Module Stabilization and Validation Enhancements | Kadarkarai | 2026-09-19 |  | Not Started
M-23 | Critical: Achievo Mobile App Upgrades and Store Policy Compliance Upda | MJ | 2026-09-12 |  | Not Started
Formulas:
Delay (days) = IF([Actual Date]<>"",[Actual Date]-[Planned Date],IF(AND([Planned Date]<TODAY(),[Status]<>"Completed"),TODAY()-[Planned Date],0))
Upcoming within 14 days = IF(AND([Planned Date]>=TODAY(),[Planned Date]<=TODAY()+14,[Status]<>"Completed"),"YES","")

## Risks & Issues
RISKS & ISSUES REGISTER
Severity = Impact × Probability (formula). High severity auto-highlighted.
Risk ID | Description | Impact | Probability | Severity | Owner | Mitigation | Status | Review Date
R-01 | CS 1.0 decommission (BRIKS / Coupon / OTP) may disrupt CS 2.0 dual-run | High | High |  | MJ | Owned by MJ; track in weekly governance; link to FY27 V1 source items. | Open | 2026-08-03
R-02 | ERP / Salesforce connector scope (CS 2.0) under-estimated vs. planned hours | High | Medium |  | MJ | Owned by MJ; track in weekly governance; link to FY27 V1 source items. | Watching | 2026-08-17
R-03 | PIS Journey Builder prediction agents depend on unstable partner data quality | High | High |  | MJ | Owned by MJ; track in weekly governance; link to FY27 V1 source items. | Mitigating | 2026-08-10
R-04 | Internal VAPT + remediation capacity contention with feature delivery | Medium | High |  | Jawahar | Owned by Jawahar; track in weekly governance; link to FY27 V1 source items. | Open | 2026-09-05
R-05 | Include=Pending items without decision are inflating Q1 commitment risk | High | Medium |  | MJ | Owned by MJ; track in weekly governance; link to FY27 V1 source items. | Open | 2026-09-08
R-06 | TBD-hour items prevent reliable capacity & burn forecasting | Medium | High |  | MJ | Owned by MJ; track in weekly governance; link to FY27 V1 source items. | Open | 2026-08-04
R-07 | CS 2.0 Core tech maintenance backlog crowding new-feature sprints | High | Medium |  | MJ | Owned by MJ; track in weekly governance; link to FY27 V1 source items. | Open | 2026-08-07
R-08 | Achievo / Rewards stream under-staffed relative to CS 2.0 Achievo scope | Medium | Medium |  | MJ | Owned by MJ; track in weekly governance; link to FY27 V1 source items. | Mitigating | 2026-08-16
R-09 | Q1 Critical mass may create spillover into Q2 without rebaseline | High | High |  | Jawahar | Owned by Jawahar; track in weekly governance; link to FY27 V1 source items. | Open | 2026-09-06
R-10 | Cross-project dependency chains (same-owner serial work) create idle wait | Medium | Medium |  | Jawahar | Owned by Jawahar; track in weekly governance; link to FY27 V1 source items. | Mitigating | 2026-09-05
R-11 | Description gaps on large-hour items reduce estimate confidence | Low | Medium |  | MJ | Owned by MJ; track in weekly governance; link to FY27 V1 source items. | Open | 2026-08-16
R-12 | Mobile / Core / Data flag sparsity weakens workstream reporting | Low | Low |  | Shriguru | Owned by Shriguru; track in weekly governance; link to FY27 V1 source items. | Open | 2026-09-08
R-13 | Production support interrupts may steal CS 2.0 Core capacity | Medium | High |  | MJ | Owned by MJ; track in weekly governance; link to FY27 V1 source items. | Watching | 2026-08-02
R-14 | Compliance / VAPT findings late in quarter threaten release gates | High | Medium |  | MJ | Owned by MJ; track in weekly governance; link to FY27 V1 source items. | Mitigating | 2026-08-29
R-15 | Unassigned project rows in source need owner clarification | Medium | Low |  | Kadarkarai | Owned by Kadarkarai; track in weekly governance; link to FY27 V1 source items. | Watching | 2026-08-19
R-18 | Delivery risk linked from tracker tasks (R-18) | High | Medium |  | Jawahar | Review linked tasks; confirm Include and dates. | Open | 2026-08-09
R-19 | Delivery risk linked from tracker tasks (R-19) | High | Medium |  | Jawahar | Review linked tasks; confirm Include and dates. | Open | 2026-08-09
R-20 | Delivery risk linked from tracker tasks (R-20) | High | Medium |  | Jawahar | Review linked tasks; confirm Include and dates. | Open | 2026-08-09

## Dependencies
DEPENDENCIES REGISTER
Overdue dependencies (Expected Date < TODAY and Status ≠ Satisfied) are highlighted.
Dependency ID | Task | Depends On | Owner | Expected Date | Actual Date | Status
D-001 | T-002 | T-001 | MJ | 2026-09-28
D-002 | T-003 | T-002 | MJ | 2026-07-23
D-003 | T-004 | T-003 | MJ | 2026-08-08
D-004 | T-005 | T-004 | MJ | 2026-08-10
D-005 | T-007 | T-006 | MJ | 2026-09-26
D-006 | T-008 | T-007 | MJ | 2026-08-29
D-007 | T-009 | T-008 | MJ | 2026-09-04
D-008 | T-010 | T-009 | Jawahar | 2026-08-27
D-009 | T-011 | T-010 | Jawahar | 2026-09-12
D-010 | T-012 | T-011 | MJ | 2026-09-19
D-011 | T-013 | T-012 | MJ | 2026-07-14
D-012 | T-014 | T-013 | MJ | 2026-09-21
D-013 | T-016 | T-015 | MJ | 2027-02-01
D-014 | T-017 | T-016 | MJ | 2027-06-06
D-015 | T-018 | T-017 | MJ | 2027-05-02
D-016 | T-019 | T-018 | MJ | 2027-05-20
D-017 | T-020 | T-019 | MJ | 2027-05-13
D-018 | T-021 | T-020 | MJ | 2027-06-15
D-019 | T-022 | T-021 | MJ | 2027-06-02
D-020 | T-024 | T-023 | Shriguru | 2026-08-22
D-021 | T-025 | T-024 | Shriguru | 2026-07-15
D-022 | T-026 | T-025 | Shriguru | 2026-09-22
D-023 | T-027 | T-026 | Shriguru | 2026-09-06
D-024 | T-028 | T-027 | Shriguru | 2026-07-22
D-025 | T-029 | T-022 | MJ | 2027-05-30
D-026 | T-031 | T-030 | MJ | 2026-09-23
D-027 | T-032 | T-031 | MJ | 2026-09-13
D-028 | T-033 | T-032 | Jawahar | 2026-09-19
D-029 | T-034 | T-033 | Jawahar | 2026-09-14
D-030 | T-035 | T-034 | Jawahar | 2026-09-12
D-031 | T-036 | T-035 | MJ | 2026-09-27
D-032 | T-037 | T-036 | MJ | 2026-08-21
D-033 | T-038 | T-037 | Jawahar | 2026-08-01
D-034 | T-039 | T-038 | Jawahar | 2026-08-18
D-035 | T-040 | T-039 | Jawahar | 2026-09-19
D-036 | T-041 | T-040 | Jawahar | 2026-08-20
D-037 | T-042 | T-041 | Jawahar | 2026-09-25
D-038 | T-043 | T-042 | Kadarkarai | 2026-08-14
D-039 | T-044 | T-043 | Kadarkarai | 2026-09-28
D-040 | T-045 | T-044 | Jawahar | 2026-08-13
D-041 | T-046 | T-045 | Jawahar | 2026-08-17
D-042 | T-047 | T-046 | Jawahar | 2026-07-13
D-043 | T-048 | T-047 | Jawahar | 2026-07-20
D-044 | T-050 | T-049 | MJ | 2026-11-02
D-045 | T-051 | T-050 | Jawahar | 2026-11-15
D-046 | T-052 | T-051 | Jawahar | 2026-12-21
D-047 | T-053 | T-052 | Jawahar | 2026-10-18
D-048 | T-054 | T-053 | Jawahar | 2026-12-11
D-049 | T-055 | T-054 | Jawahar | 2026-11-20
D-050 | T-056 | T-055 | Jawahar | 2026-10-27
D-051 | T-057 | T-056 | Jawahar | 2026-12-14
D-052 | T-058 | T-057 | Jawahar | 2026-10-07
D-053 | T-059 | T-058 | Jawahar | 2026-10-28
D-054 | T-060 | T-059 | MJ | 2026-12-07
D-055 | T-061 | T-060 | MJ | 2026-12-27
D-056 | T-062 | T-061 | MJ | 2026-11-02
D-057 | T-063 | T-062 | MJ | 2026-12-22
D-058 | T-064 | T-063 | MJ | 2026-12-17
D-059 | T-065 | T-064 | MJ | 2026-11-09
D-060 | T-066 | T-065 | Jawahar | 2026-11-24
D-061 | T-068 | T-067 | Jawahar | 2027-03-28
D-062 | T-069 | T-068 | Jawahar | 2027-02-01
D-063 | T-070 | T-069 | Jawahar | 2027-02-06
D-064 | T-071 | T-070 | Jawahar | 2027-03-22
D-065 | T-072 | T-071 | Jawahar | 2027-02-21
D-066 | T-073 | T-072 | Jawahar | 2027-02-17
D-067 | T-074 | T-073 | Jawahar | 2027-03-27
D-068 | T-075 | T-074 | Jawahar | 2027-03-10
D-069 | T-076 | T-075 | Jawahar | 2027-02-19
D-070 | T-077 | T-076 | MJ | 2027-03-08
D-071 | T-078 | T-077 | MJ | 2027-02-16
D-072 | T-079 | T-078 | MJ | 2027-02-26
D-073 | T-081 | T-080 | Jawahar | 2027-06-20
D-074 | T-082 | T-081 | Jawahar | 2027-05-07
D-075 | T-083 | T-082 | Jawahar | 2027-05-20
D-076 | T-084 | T-083 | Jawahar | 2027-06-05
D-077 | T-085 | T-084 | Jawahar | 2027-05-24
D-078 | T-086 | T-085 | Jawahar | 2027-06-05
D-079 | T-087 | T-086 | Jawahar | 2027-05-18
D-080 | T-089 | T-088 | Siva | 2026-08-17
D-081 | T-090 | T-089 | Siva | 2026-09-08
D-082 | T-091 | T-090 | Siva | 2026-09-26
D-083 | T-092 | T-091 | Siva | 2026-08-05
D-084 | T-093 | T-092 | Siva | 2026-12-03
D-085 | T-094 | T-093 | Siva | 2026-12-06
D-086 | T-095 | T-094 | Siva | 2026-11-07
D-087 | T-096 | T-095 | Siva | 2026-12-13
D-088 | T-097 | T-096 | Siva | 2026-11-08
D-089 | T-098 | T-097 | Siva | 2026-12-14
D-090 | T-099 | T-098 | Siva | 2026-12-19
D-091 | T-100 | T-099 | Siva | 2027-02-10
D-092 | T-101 | T-100 | Siva | 2027-02-21
D-093 | T-102 | T-101 | Siva | 2027-03-16
D-094 | T-103 | T-102 | Siva | 2027-06-26
D-095 | T-104 | T-103 | Siva | 2027-06-27
D-096 | T-105 | T-104 | Siva | 2027-06-20
D-097 | T-107 | T-106 | Kadarkarai | 2026-09-06
D-098 | T-108 | T-107 | Kadarkarai | 2026-09-06
D-099 | T-109 | T-108 | Kadarkarai | 2026-08-20
Formulas:
Status = IF([Actual Date]<>"","Satisfied",IF([Expected Date]<TODAY(),"Overdue","Open"))

## Lookup Lists
LOOKUP LISTS — Dropdown Source Values
Maintain these lists to drive Project Tracker dropdowns and named ranges.
Owners | Priority | Status | Teams | Projects | Releases | Sprint | Phase | Workstream | Impact | Probability | Risk Status | Dep Status | Category
Jawahar | Critical | Not Started | Platform | CS 1.0 | R26.Q1 | Sprint 01 | Discovery | Product Delivery | High | High | Open | Open | Funct Enhance
Kadarkarai | High | In Progress | Core Product | CS 2.0 | R26.Q2 | Sprint 02 | Design | Platform | Medium | Medium | Mitigating | Satisfied | Maintenance
MJ | Medium | Completed | Rewards | CS 2.0 Achievo | R26.Q3 | Sprint 03 | Build | Data | Low | Low | Watching | Overdue | New Features
Shriguru | Low | At Risk | Data & AI | CS 2.0 Core | R26.Q4 | Sprint 04 | Test | Integrations |  |  | Closed | Waived | PIS New Feature
Siva |  | Blocked | Integrations | CS 2.0 Data | R27.Q1 | Sprint 05 | UAT | Reliability |  |  |  |  | Tech Enhance
|  |  | SRE / Support | Unassigned | R27.Q2 | Sprint 06 | Release | Governance |  |  |  |  | Tech Maintenance
|  |  | Architecture |  | Hotfix | Sprint 07 | Hypercare | Tech Debt
|  |  | Compliance Eng |  | N/A | Sprint 08
Sprint 09
Sprint 10
Sprint 11
Sprint 12
Sprint 13
Sprint 14
Sprint 15
Sprint 16
Sprint 17
Sprint 18
Sprint 19
Sprint 20
Sprint 21
Sprint 22
Sprint 23
Sprint 24
Sprint 25
Sprint 26